## FY10 Totals
Project Automation - FY 2010
| Test Cases |  | Q1 | Q2 | Q3 | Q4 | Total Scripts | % FY2010 Automation | Total Project Automation |  | Automation to Date
Automation Type | WinR | New TC | TS | TS | TS | TS | FY 2010 |  | TC | TS
MAP - Pro/JCL | 285 | 0 | 21 | 0 | 0 | 0 | 21 | 7.368% | 285 | 253 | 88.77%
MAP - Info/Xe | 173 | 2 | 4 | 71 | 0 | 0 | 75 | 42.86% | 175 | 77 | 44%
Totals | 458 | 2 | 25 | 71 | 0 | 0 | 96 | 20.87% | 460 | 330 | 71.74%
Totals for each Automation Developer
| Test Cases |  | Q1 | Q2 | Q3 | Q4 | Total Scripts | % FY2010 Automation | Developer Totals |  | Automation by Developer
Developer | WinR | New TC | TS | TS | TS | TS | FY 2010 |  | TC | TS
Claudie | 368 | 1 | 24 | 62 | 0 | 0 | 86 | 23.31% | 369 | 318 | 86.18%
Lisa | 90 | 0 | 1 | 11 | 0 | 0 | 10 | 11.11% | 90 | 10 | 11.11%
Scott | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Totals | 458 | 1 | 25 | 73 | 0 | 0 | 96 | 20.92% | 459 | 328 | 71.46%

## FY2010 Coverage
Automation Type | Product | Area Covered | Owner | WinRunner Cases | New Test Cases | Scripts Q1 | Scripts Q2 | Scripts Q3 | Scripts Q4 | Scripts FY10 | Total Scripts | % complt
MAP | Pro/JCL | Admin | Claudie | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 85.7143
MAP | Pro/JCL | Help | Claudie | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 100
MAP | Pro/JCL | JJ | Claudie | 50 | 0 | 1 | 0 | 0 | 0 | 1 | 49 | 98
MAP | Pro/JCL | JJDirect | Claudie | 15 | 0 | 4 | 0 | 0 | 0 | 4 | 13 | 86.6667
MAP | Pro/JCL | JJScan | Claudie | 3 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 100
MAP | Pro/JCL | JMP | Claudie | 25 | 0 | 3 | 0 | 0 | 0 | 3 | 25 | 100
MAP | Pro/JCL | MISC | Claudie | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 71.4286
MAP | Pro/JCL | Product Usage | Claudie | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MAP | Pro/JCL | Reformat | Claudie | 20 | 0 | 1 | 0 | 0 | 0 | 1 | 16 | 80
MAP | Pro/JCL | Remote Validation | Claudie | 8 | 0 | 2 | 0 | 0 | 0 | 2 | 8 | 100
MAP | Pro/JCL | RTS | Claudie | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 85.1064
MAP | Pro/JCL | Scheduler | Claudie | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 76.9231
MAP | Pro/JCL | Selection Exit | Claudie | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100
MAP | Pro/JCL | Selection List | Claudie | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 85.7143
MAP | Pro/JCL | Shared | Claudie | 7 | 0 | 6 | 0 | 0 | 0 | 6 | 6 | 85.7143
MAP | Pro/JCL | STC | Claudie | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 100
MAP | Pro/JCL | System | Claudie | 8 | 0 | 1 | 0 | 0 | 0 | 1 | 5 | 62.5
MAP | Pro/JCL | Validation | Claudie | 38 | 0 | 1 | 0 | 0 | 0 | 1 | 35 | 92.1053
QTP | Pro/JCL | Customize | Scott
QTP | Pro/JCL | JCL Editor | Scott
QTP | Pro/JCL | JMP | Scott
QTP | Pro/JCL | Local Scan | Scott
QTP | Pro/JCL | Mainframe Scan | Scott
|  | Summary |  | 285 | 0 | 21 | 0 | 0 | 0 | 21 | 253
MAP | INFOX | A_NISSAN_263 | Lisa | 6 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 16.6667
| INFOX | QUERY1 | Lisa | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| INFOX | REPORTS | Lisa | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| INFOX | SETUP1 | Lisa | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| INFOX | UPDATE1 | Lisa | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| INFOX | XREF_CICSGROUP1 | Lisa | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| INFOX | XREF_CICSTRANSACTION1 | Lisa | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| INFOX | XREF_DB2COLLECTIONID1 | Lisa | 2 | 1 | 0 | 3 | 0 | 0 | 3 | 3 | 150
| INFOX | XREF_DB2PACKAGE1 | Lisa | 3 | 0 | 0 | 2 | 0 | 0 | 2 | 2 | 66.6667
| INFOX | XREF_DB2PLAN1 | Lisa | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 50
| INFOX | XREF_DB2TABLE1 | Lisa | 3 | 0 | 0 | 2 | 0 | 0 | 2 | 2 | 66.6667
| INFOX | XREF_DSNAME1 | Lisa | 4 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 25
| INFOX | ADMINISTRATOR | Claudie | 12 | 0 | 3 | 7 | 0 | 0 | 10 | 10 | 83.3333
| INFOX | XREF_JOB1 | Claudie | 10 | 0 | 0 | 9 | 0 | 0 | 9 | 9 | 90
| INFOX | FOLDERS | Claudie | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 2 | 100
| INFOX | MISC1 | Claudie | 8 | 0 | 0 | 5 | 0 | 0 | 5 | 5 | 62.5
| INFOX | PRINTSETUP | Claudie | 10 | 0 | 0 | 9 | 0 | 0 | 9 | 9 | 90
| INFOX | SORTS | Claudie | 2 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 50
| INFOX | XREF1 | Claudie | 10 | 0 | 0 | 9 | 0 | 0 | 9 | 9 | 90
| INFOX | XREF_JOB2 | Claudie | 11 | 0 | 0 | 8 | 0 | 0 | 8 | 8 | 72.7273
| INFOX | XREF_PGM1 | Claudie | 9 | 0 | 0 | 7 | 0 | 0 | 7 | 7 | 77.7778
| INFOX | XREF_PROC1 | Claudie | 5 | 0 | 0 | 5 | 0 | 0 | 5 | 5 | 100
| INFOX | XREF_SYSOUT1 | Claudie | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| INFOX | [8 empty] | 0
|  | Summary |  | 173 | 2 | 4 | 71 | 0 | 0 | 75 | 75
|  | Total Automation |  | 458 | 2 | 25 | 71 | 0 | 0 | 96 | 328
|  | Automation by Analyst | Claudie | 368 | 1 | 24 | 62 | 0 | 0 | 86 | 318
|  |  | Scott | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Lisa | 90 | 1 | 1 | 11 | 0 | 0 | 10 | 10

## Coverage-Detail-ProJcl-2010
|  |  | Converted | New | [5 empty] | Code | Script
Total for Suite |  | WinRunner Scripts | to MAP | Script | Date | Analyst | Quarter 2010 | Analyst/Qtr | Comments | Review | P/F/I | Date | Analyst | Notes
ADMIN1:
|  | PD1B006 | X |  | 2009-01-09 | LisaC
|  | PH35055 |  |  | 2009-02-02 | LisaC |  |  | need function to handle parameter tables
|  | PH43055 | X |  | 2009-08-21 | cjm |  |  | need function to check cursor position
|  | PH15034 | X |  | 2009-08-19 | LisaC |  |  | waiting for 'presskey' function & function to handle popup panel w/ no scroll field
|  | PH49014 | X |  | 2009-08-20 | cjm
|  | PH48002 | X |  | 2009-08-21 | cjm
|  | PH16071 | X |  | 2009-08-24 | cjm
7 |  |  |  | 0
HELP1:
|  | HELP_ADMINISTRATION | X |  | 2009-05-04 | cjm |  |  | D0JHDIA3.txt has 2 panel ID (the first panel and the superimposed popup panelid)
|  | HELP_JMP_SETTINGS | X |  | 2009-08-24 | cjm
|  | HELP_MAINMENU | X |  | 2009-05-05 | cjm
|  | HELP_REFORMATTER | X |  | 2009-05-20 | cjm
|  | HELP_REFORMATTER_STATEMENTS | X |  | 2009-05-20 | cjm
|  | HELP_RTS_SETTINGS | X |  | 2009-05-05 | cjm
6
HELP2:
|  | P12738 | X |  | 2009-05-28 | cjm
|  | P13219 | X |  | 2009-05-28 | cjm
|  | PC11012 | X |  | 2009-05-28 | cjm |  |  | capture Reformat DD help panel D0SHREF3 has extra blank pages at the bottom.
|  | PH22125 | X |  | 2009-06-01 | cjm
|  | PH25112 | X |  | 2009-06-01 | cjm
|  | PH2C051 | X |  | 2009-06-01 | cjm
|  | PH43053 | X |  | 2009-06-02 | cjm |  |  | Test for copyright failed opening Impact ticket: 683536
|  | P685586 | X |  | 2009-11-09 | cjm |  |  | New testcase PR290
8 |  |  |  | 0
JJ1
|  | P10927 | X |  | 2009-02-26 | cjm
|  | P11135 | X |  | 2009-01-29 | LisaC
|  | P11573 | X |  | 2009-02-25 | cjm
|  | P12455 | X |  | 2009-02-25 | cjm
|  | P12479 | X |  | 2009-02-26 | cjm
|  | P12783 | X |  | 2009-02-25 | cjm
|  | P13394 | X |  | 2009-12-02 | cjm
|  | PC24008 | X |  | 2009-02-27 | cjm
|  | PH11081 | X |  | 2009-12-03 | cjm
|  | PH11083 | X |  | 2009-02-27 | cjm
|  | PH12020 | X |  | 2009-02-24 | cjm
|  | PH22137 | X |  | 2009-02-24 | cjm
|  | PH28151 | X |  | 2009-09-23 | cjm |  |  | need to check direct execution jmp messages/added p106089
|  | PH29030 | X |  | 2009-02-26 | cjm
|  | PH29034 | X |  | 2009-02-25 | cjm
|  | PH2A021 | X |  | 2009-02-25 | cjm
|  | PC1A018 | X |  | 2009-03-02 | cjm
|  | PR13295 | X |  | 2009-02-24 | cjm
18
JJ2
|  | P665386 | X | \ | 2009-11-16 | cjm |  |  | new script added on PR290
|  | PC38013 | X |  | 2009-02-21 | cjm
|  | PC5B001 | [6 empty] | Checking for a B37 (may take too long to run).
|  | PH21085 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH35063 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PR10126 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PR12783 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PR12988 | X |  | 2009-02-24 | cjm |  |  |  | skb
|  | PR13084 | X |  | 2009-02-03 | cjm |  |  |  | skb
|  | PR13123 | X |  | 2009-03-02 | cjm |  |  | use verifyPopup. COMPLETED/ Needs review
|  | PR13225 | X |  | 2009-02-05 | cjm |  |  |  | skb
|  | PR13272 | X |  | 2009-02-09 | cjm |  |  |  | skb
|  | PR13398 | X |  | 2009-02-10 | cjm |  |  |  | skb
|  | PC1C002 | X |  | 2009-02-11 | cjm |  |  |  | skb
|  | PU16004 | X |  | 2009-02-11 | cjm |  |  |  | skb
|  | PU1C007 | X |  | 2009-02-11 | cjm |  |  |  | skb
|  | PC38001 | X |  | 2/24.2009 | cjm |  |  | This script needs to run TZ17A because of Migrated dataset. | skb
|  | PH3C024 | X |  | 2009-02-12 | cjm |  |  |  | skb
|  | PC3B013 | X |  | 2009-02-19 | cjm |  |  |  | skb
|  | PH39099 | X |  | 2009-02-20 | cjm |  |  |  | skb
|  | PH43180 | X |  | 2009-02-20 | cjm |  |  |  | skb
|  | PH42017 | X |  | 2009-02-20 | cjm |  |  |  | skb
|  | PH43112 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH43054 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH3A067 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH42016 | X |  | 2010-01-27 | cjm | Q1 | ClaudieQ1
|  | PH3A015 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH3A059 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH3A062 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH3A065 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH3A114 | X |  | 2009-02-24 | cjm |  |  |  | skb
|  | PH49013 | X |  | 2009-02-24 | cjm |  |  |  | skb
32 |  |  |  | 0
JJDIRECT1
|  | PH28086 | X |  | 2010-01-28 | cjm | Q1 | ClaudieQ1
|  | PH29103 | X |  | 2009-09-02 | cjm
|  | PH34042 | I |  | 2010-01-27 | cjm
|  | PD29007 | X |  | 2009-06-30 | cjm
|  | PH2A147 | X |  | 2009-07-01 | cjm
|  | PH2A157 | X |  | 2009-07-06 | cjm
|  | PH3A115 | X |  | 2009-07-07 | cjm
|  | PD28006 | X |  | 2010-01-28 | cjm | Q1 | ClaudieQ1 | when capturing report bottom of data does not show up .
|  | PH44080 | X |  | 2009-06-29 | cjm
|  | PH4C001 | X |  | 2009-06-29 | cjm
|  | PU4B014 | X |  | 2009-07-01 | cjm
PU42008
|  | PH43016 | X |  | 2010-02-25 | cjm | Q1 | ClaudieQ1
|  | PH48003 | X |  | 2010-03-08 | cjm | Q1 | ClaudieQ1
|  | PH48030 | X |  | 2009-06-24 | cjm
15 |  |  |  | 0
JJSCAN1:
|  | PC26009 | X |  | 2010-03-08 | cjm | Q1 | ClaudieQ1 | Need to capture SJL DNS
|  | PH11087 | X |  | 2009-07-08 | cjm
|  | PR13125 | X |  | 3/2/20009 | cjm
3 |  |  |  | 0
JMP1:
|  | PC2A010 | X |  | 2009-04-27 | cjm |  |  | fixed by skb Multiple field with the same name on form
|  | PU4A010 | X |  | 2009-04-27 | cjm
|  | PH41001 | X |  | 2009-04-28 | cjm
|  | PR12492 | X |  | 2009-04-29 | cjm
|  | PH13056 | X |  | 2009-04-30 | cjm
|  | PH35040 | X |  | 2009-05-27 | cjm |  |  | fixed by skb
|  | PU29009 | X |  | 2009-06-02 | skb
|  | PH12043 | X |  | 2009-06-10 | cjm
|  | PH24088 | X |  | 2009-06-10 | cm
|  | PH26061 | X |  | 2009-06-10 | cjm
|  | PH27044 | X |  | 2009-06-11 | cjm
|  | PR12540 | X |  | 2009-06-11 | cjm
|  | PH35015 | X |  | 2009-06-11 | cjm
|  | PH39104 | X |  | 2009-06-11 | cjm
|  | PU14008 | X |  | 2009-06-11 | cjm
|  | PH37022 | X |  | 2009-06-11 | cjm
|  | PH42110 | X |  | 2009-06-11 | cjm
|  | PU4B007 | X |  | 2009-06-15 | cjm
|  | PH51010 | X |  | 2009-06-15 | cjm
|  | P662041 | X |  | 2009-10-15 | cjm |  |  | PR290 new script
|  | P687454 | X |  | 2009-11-10 | cjm
|  | PH27059 | X |  | 2010-03-02 | cjm | Q1 | ClaudieQ1
|  | PC35004 | X |  | 2010-03-04 | cjm | Q1 | ClaudieQ1 | need to delete ID.SJL.TEMP*
|  | SR11048 | X |  | 2010-03-08 | cjm | Q1 | ClaudieQ1
|  | PH21117 | X |  | 6/15.2009 | cjm |  |  | Need Model panel to be installed
25 |  |  |  | 0
MISC1:
|  | PH41037 | [6 empty] | Need to have libraries allocated for one release and calling a different release
PH31025
7 |  |  |  | 0
PRODUCT USAGE:
PH45030
1 |  |  |  | 0
REFORMAT1:
|  | PH25013 | X |  | 2009-06-04 | skb
|  | P11706 | X |  | 2010-03-04 | cjm | Q1 | ClaudieQ1
|  | PC25013 | X |  | 6/23/20009 | cjm
|  | PH12015 | X |  | 2009-06-24 | cjm
PH13023
|  | PR10495 | X |  | 2009-06-24 | cjm
|  | PR10516 | X |  | 2009-06-23 | cjm
|  | PC25015 | X |  | 2009-06-23 | cjm
|  | PT0262 | X |  | 2009-06-22 | cjm |  |  | need to check why enable reformat does not stay to N for If statement
|  | PH43124 | X |  | 2009-06-18 | cjm
|  | PH3A082 | [6 empty] | ISPF statistics
|  | PH33064 | [6 empty] | Loop to work on reformat
|  | P10715 | X |  | 2009-06-18 | cjm
|  | P100109 | X |  | 2009-06-18 | cjm
|  | PH12083 | X |  | 2009-06-16 | cjm
|  | PH41079 | X |  | 2009-06-16 | cjm
PH4C029
|  | PH56048 | X |  | 2009-06-16 | cjm
|  | PH57007 | X |  | 2009-06-15 | cjm
|  | P103451 | X |  | 2009-09-23 | cjm |  |  | new script for 290
20 |  |  |  | 0
REMOTE_VALIDATION1:
|  | P571146 | X |  | 2010-01-07 | cjm | Q1 | ClaudieQ1 | new script for 290
|  | PH43167 | X |  | 2009-07-25 | cjm |  |  | Need to remove the "forced enter" on panelListAction function to capture a Help Screen for Direct execution Select help panel..
|  | PH43023 | X |  | 2009-09-02 | cjm
|  | PH43018 | X |  | 2009-09-02 | cjm
|  | PH43091 | X |  | 2009-09-03 | cjm
|  | PH43097 | X |  | 2009-09-03 | cjm
|  | PH43027 | X |  | 2009-09-03 | cjm
|  | PR98118 | X |  | 2010-01-12 | cjm | Q1 | ClaudieQ1 | new script for 290
8 |  |  |  | 0
RTS1:
|  | P106892 | X |  | 2009-09-22 | cjm
|  | P100103 | X |  | 2009-04-28 | cjm
|  | P10883 | X |  | 2009-04-08 | cjm |  |  | Problem capture help popup / Fixed
|  | P12534 | X |  | 2009-04-14 | cjm
|  | P12671 | X |  | 2009-04-15 | cjm
|  | P12834 | X |  | 2009-04-15 | cjm
|  | PC12001 | X |  | 2009-04-15 | cjm
|  | PC21002 | [6 empty] | RMM
|  | PC22012 | X |  | 2009-04-16 | cjm
|  | PC27005 | X |  | 2009-04-16 | cjm
|  | PH12036 | X |  | 2009-04-16 | cjm
|  | PH12038 | X |  | 2009-04-28 | cjm
|  | PH16232 | X |  | 2009-04-20 | cjm
|  | PH18111 | X |  | 2009-04-20 | cjm
|  | PH22121 | X |  | 2009-04-20 | cjm
|  | PH24015 | X |  | 2009-12-02 | cjm
|  | PH25062 | X |  | 2009-04-20 | cjm
|  | PH25072 | X |  | 2009-04-20 | cjm
|  | PR10478 | X |  | 2009-12-01 | cjm
SH36067
20
RTS2:
|  | P11135 | X |  | 2009-04-21 | cjm
|  | P11316 | X |  | 2009-12-01 | cjm
|  | P13292 | X |  | 2009-04-22 | cjm
|  | PC15006 | X |  | 2009-03-24 | cjm
|  | PC26004 | X |  | 2009-03-30 | cjm
|  | PC2C003 | X |  | 2009-03-30 | cjm
PC38009
|  | PC48006 | X |  | 2009-03-31 | cjm
PC48008
|  | PC53004 | X |  | 2009-04-22 | cjm
|  | PH12124 | X |  | 2009-03-31 | cjm
|  | PH24013 | X |  | 2009-06-02 | cjm
|  | PH25019 | X |  | 2009-03-31 | cjm
PH2A130
|  | PH32016 | X |  | 2009-04-01 | cjm
|  | PH42014 | X |  | 2009-04-01 | cjm |  |  | Problems capturing help panels from popup list panel Fixed
|  | PH42059 | X |  | 2009-04-01 | cjm |  |  | blank popup panel for JCL Printing
|  | PH49001 | X |  | 2009-06-03 | skb |  |  | Looking for rts win280 and not found
|  | PR11136 | X |  | 2009-04-02 | cjm
|  | PR11382 | X |  | 2009-06-04 | skb |  |  | unable to find string on child popup
|  | PR11489 | X |  | 2009-06-04 | LisaC/skb
|  | PR11624 | X |  | 2009-04-06 | cjm |  |  | capture entire output byrun byjob…..
|  | PR11948 | X |  | 2009-04-06 | cjm
PR13170
|  | PT0970 | X |  | 2009-04-07 | cjm
|  | PU3A002 | X |  | 2009-04-07 | cjm |  |  | another strange popup within popup capture on Library type Add option
S10077
27 |  |  |  | 0
SCHEDULER1:
|  | P653071 | X |  | 2009-09-23 | cjm |  |  | New Script for 290
|  | P13378 | X |  | 2009-09-03 | cjm
|  | PC28002 | X |  | 2009-09-04 | cjm
|  | PH12007 | X |  | 2009-09-04 | cjm |  |  | Verify popup: duplicate last line of Scheduler Popup
|  | PH14059 | X |  | 2009-09-04 | cjm
|  | PH15025 | X |  | 2009-09-09 | cjm |  |  | need to check if TWS8 is up or down
|  | PH21078 | X |  | 2009-09-16 | cjm
PH2A019
|  | PH33045 | X |  | 2009-09-10 | cjm
|  | PH27003 | X |  | 2009-09-04 | cjm
|  | PH32040 | X |  | 2009-09-16 | cjm
PH23054
PH43035
PH3C059
|  | PH34010 | X |  | 2009-09-10 | cjm
|  | PC4A009 | X |  | 2009-09-14 | cjm
|  | P13192 | X |  | 2009-09-14 | cjm
|  | PH15031 | X |  | 2009-09-10 | cjm
|  | PH58032 | X |  | 2009-09-11 | cjm
|  | PH59003 | X |  | 2009-09-11 | cjm
|  | PH64037 | X |  | 2009-09-16 | cjm
|  | PU56005 | X |  | 2009-09-11 | cjm
|  | P11005 | X |  | 2009-09-11 | cjm
|  | PH12118 | X |  | 2009-09-11 | cjm
PC34009
PH15024
26 |  |  |  | 0
SELECTIONEXIT1:
|  | PC31010 | X |  | 2009-06-09 | cjm
1 |  |  |  | 0
SELECTIONLIST1:
|  | PH13031 | X |  | 2009-06-03 | cjm
PH26055
|  | PH2A145 | X |  | 2009-06-04 | cjm
|  | PH2B103 | X |  | 2009-06-04 | cjm
|  | PH27018 | X |  | 2009-06-08 | cjm
|  | PH33092 | X |  | 2009-06-08 | cjm
|  | PH39096 | X |  | 2009-06-09 | cjm
7 |  |  |  | 0
SHARED1
SH2B075
|  | SH1B067 | X |  | 2010-03-15 | cjm | q1 | ClaudieQ1
|  | SR10763 | X |  | 2010-03-16 | cjm | q1 | ClaudieQ1
|  | SH42022 | X |  | 2010-03-16 | cjm | q1 | ClaudieQ1
|  | SH3A096 | X |  | 2010-03-06 | cjm | q1 | ClaudieQ1 | popup panel is icomplete when only 1 panel and no scroll
|  | SH22158 | X |  | 2010-03-17 | cjm | q1 | ClaudieQ1
|  | SH32085 | X |  | 2010-03-17 | cjm | q1 | ClaudieQ1
7 |  |  |  | 0
STC1:
|  | PH25064 | X |  | 2010-03-03 | cjm | q1 | ClaudieQ1
1 |  |  |  | 0
SYSTEM1:
|  | P11786 | X |  | 2009-06-02 | cjm
|  | P12340 | X |  | 2009-06-02 | cjm
|  | P13357 | X |  | 2010-02-18 | cjm | q1 | ClaudieQ1
|  | PH2A146 | X |  | 2009-06-03 | cjm
|  | PH32071 | X |  | 2009-06-03 | cjm
PH39003
|  | PH43024 | [6 empty] | Need a Master and Slave up for this script
|  | PH21176 | [6 empty] | Product usage
8 |  |  |  | 0
VALIDATION1:
|  | P13028 | X |  | 2009-03-16 | cjm
|  | PH11044 | X |  | 2009-03-16 | cjm
|  | PH12062 | [6 empty] | Loop on mem list
|  | PH12091 | X |  | 2009-03-16 | cjm
|  | PH21106 | X |  | 2009-03-16 | cjm
|  | PH28049 | X |  | 2009-03-18 | cjm
|  | PH2A113 | X |  | 2009-03-16 | cjm
|  | PH2A126 | X |  | 2009-06-02 | skb |  |  | not able to capture the entire help panel. Line 73 in script
|  | PH2A155 | X |  | 2009-03-17 | cjm
|  | PH2B029 | X |  | 2009-06-02 | skb |  |  | Added the ln $status to script. Update before working on it to get updates from repo
|  | PH31032 | X |  | 2009-03-17 | cjm
|  | PH36040 | X |  | 2009-03-17 | cjm
|  | PR100036 | X |  | 2009-04-21 | cjm |  |  | Would need toe rerun (capture Option Report / Missing popup title)
|  | PR10551 | X |  | 2009-03-19 | cjm |  |  | You must have rts member pjgl0020 for this test to run.
|  | PH47009 | X |  | 2009-07-09 | cjm
|  | PH43104 | X |  | 2009-04-22 | cjm |  |  | TESTING PCFILE RESTORE AFTER ADDING A MACHINE DEFINITION
|  | PH44019 | X |  | 2009-03-17 | cjm
17 |  |  |  | 0
VALIDATION2:
|  | PR11725 | X |  | 2009-03-02 | cjm
|  | PR12777 | X |  | 2009-03-02 | cjm
|  | PR13147 | X |  | 2009-03-02 | cjm
|  | PT1279 | X |  | 2009-03-03 | cjm
|  | PC2C004 | X |  | 2009-03-13 | cjm
|  | PU1A002 | X |  | 2009-03-04 | cjm
PH13009
|  | PH3A112 | X |  | 2009-03-13 | cjm
|  | PH33049 | X |  | 2010-02-18 | cjm | q1 | ClaudieQ1
|  | PH59059 | X |  | 2009-03-24 | cjm
|  | PH24071 | X |  | 2009-03-05 | cjm |  |  | Added pcfile reset
|  | PR10169 | X |  | 2009-03-05 | cjm |  |  | Problem capturing screen messages/fixed by capturing SJL instead. | Fixed/Modified to MAP- messages during busy not supported in MAP.
|  | PH42031 | X |  | 2009-03-10 | cjm
|  | PH42007 | [6 empty] | OPC
|  | PH24068 | X |  | 2009-03-10 | cjm
|  | PH43129 | X |  | 2009-03-11 | cjm
|  | P12144 | X |  | 2009-03-16 | cjm
|  | P11999 | X |  | 2009-03-11 | cjm
|  | PC31015 | X |  | 2009-04-21 | cjm
|  | PH31113 | X |  | 2009-03-11 | cjm
|  | PH38049 | X |  | 2009-03-23 | cjm |  |  |  | Fixed/ Script still needs to be finished. | F | 2009-03-20 | skb
21 |  |  |  | 0
|  | Total number of scripts to convert | 285
|  | # of scripts converted to date | 248
|  | % complete | 87.02%
|  | # Of New Scritps | 0
|  | Remaining Scripts | 285
21 |  | Total for ClaudieQ1
0 |  | Total for ClaudieQ2
0 |  | Total for ClaudieQ3
0 |  | Total for ClaudieQ4
0 |  | Total for LisaQ1
0 |  | Total for LisaQ2
0 |  | Total for LisaQ3
0 |  | Total for LisaQ4
0 |  | Total for ScottQ1
0 |  | Total for ScottQ2
0 |  | Total for ScottQ3
0 |  | Total for ScottQ4

## Coverage-Detail-Infox-2010
Suite Totals | Suite | Test Case Document | Converted to MAP | New Scripts | Date | Analyst/Qtr | Quarter | Estimated Time | Actual Time | Lisa Est. Time | Claudie Est. Time | Comments | Comments
Lisa | A_NISSAN_263
|  | IC53007 | Y |  |  | LisaQ1 | Q1 | 4
|  | IH54039 | [5 empty] | 4 |  |  |  | scott
|  | IC55006 | [5 empty] | 4
|  | IC53008 | [5 empty] | 4
|  | IC55010 | [5 empty] | 4
|  | IH54029 | [5 empty] | 4 |  | 24
6 |  |  |  | 0
Lisa | QUERY1
|  | IH4B026 | in progress |  |  |  |  | 2
|  | I12602 | [5 empty] | 2
|  | I12628 | [5 empty] | 2
|  | I12757 | [5 empty] | 2
|  | IH11020 | [5 empty] | 2
|  | IH1A166 | [5 empty] | 2
|  | IH55035 | [5 empty] | 2
|  | IU3A008 | [5 empty] | 2
|  | IM92355 | [5 empty] | 2
|  | PIQRY001 | [5 empty] | 2 |  | 20
10
Lisa | REPORTS |  |  | 0
|  | IH54031 | [5 empty] | 2
|  | IC11025 | [5 empty] | 2
|  | IC18007 | [5 empty] | 2
|  | IC1C005 | [5 empty] | 2
|  | IC27001 | [5 empty] | 2
|  | ID12008 | [5 empty] | 2
|  | ID12010 | [5 empty] | 2
|  | IH12106 | [5 empty] | 2
|  | IH1C035 | [5 empty] | 2
|  | IH1C071 | [5 empty] | 2
|  | IH23036 | [5 empty] | 2
|  | IH48031 | [5 empty] | 2
|  | IH48061 | [5 empty] | 2
|  | IH48075 | [5 empty] | 2
|  | IH49074 | [5 empty] | 2
|  | IH4B045 | [5 empty] | 2
|  | IH52016 | [5 empty] | 2
|  | IH54012 | [5 empty] | 2
|  | IH55012 | [5 empty] | 2
|  | IH55054 | [5 empty] | 2
|  | IM92493 | [5 empty] | 2 |  | 44
|  | IM92538 | [5 empty] | 2
22 |  |  |  | 0
Lisa | SETUP1
|  | IH48072 | [5 empty] | 2
|  | IC1B003 | [5 empty] | 2
|  | IH12135 | [5 empty] | 2
|  | IH13027 | [5 empty] | 2
|  | IH16065 | [5 empty] | 2
|  | IH1A097 | [5 empty] | 2
|  | IH35079 | [5 empty] | 2
|  | IH35079 | [5 empty] | 2
|  | IH3B034 | [5 empty] | 2
|  | IH46012 | [5 empty] | 2
|  | IH48060 | [5 empty] | 2
|  | IH49009 | [5 empty] | 2
|  | IH4A031 | [5 empty] | 2
|  | IH4A047 | [5 empty] | 2
|  | IH4B007 | [5 empty] | 2
|  | IH4C014 | [5 empty] | 2
|  | IH52034 | [5 empty] | 2
|  | IM92078 | [5 empty] | 2
|  | IM108845 | [5 empty] | 2
|  | P695135 | [5 empty] | 2 |  | 40
20 |  |  |  | 0
Lisa | UPDATE1
|  | IH54062 | [5 empty] | 2
|  | I11903 | [5 empty] | 2
|  | IC1A023 | [5 empty] | 2
|  | IH12176 | [5 empty] | 2
|  | IH12235 | [5 empty] | 2
|  | IH16064 | [5 empty] | 2
|  | IH16151 | [5 empty] | 2
|  | IH21101 | [5 empty] | 2
|  | IH25016 | [5 empty] | 2
|  | IH25036 | [5 empty] | 2
|  | IH3A127 | [5 empty] | 2
|  | IH3C036 | [5 empty] | 2 |  | 24
12 |  |  |  | 0
Lisa | XREF_CICSGROUP1
|  | IH36024 | [5 empty] | 2
|  | IH46042 | [5 empty] | 2 |  | 4
2 |  |  |  | 0
Lisa | XREF_CICSTRANSACTION1
|  | IH1A028 | [5 empty] | 2
|  | IH35045 | [5 empty] | 2
|  | IH39102 | [5 empty] | 2
|  | IM91489 | [5 empty] | 2 |  | 8
4 |  |  |  | 0
Lisa | XREF_DB2COLLECTIONID1
|  | IM92010 | Y |  |  | LisaQ2 | Q2 | 2
|  | PIXRF008 | Y |  |  | LisaQ2 | Q2 | 2 |  | 4
|  | PI106569 | Y | Y |  | LisaQ2 | Q2 | 2 |  | 4
2 |  |  |  | 1 |  | LisaQ2
Lisa | XREF_DB2PACKAGE1
|  | IH13043 | Y |  |  | LisaQ2 | Q2 | 2
|  | IH12046 | Y |  |  | LisaQ2 | Q2 | 2
|  | PIXRF009 | [5 empty] | 2 |  | 6
3 |  |  |  | 0
Lisa | XREF_DB2PLAN1
|  | IM91549 | Y |  |  | LisaQ2 | Q2 | 2
|  | PIXRF007 | [5 empty] | 2 |  | 4
2 |  |  |  | 0
Lisa | XREF_DB2TABLE1
|  | ID25008 | Y |  |  | LisaQ2 | Q2 | 2
|  | IM90400 | Y |  |  | LisaQ2 | Q2 | 2
|  | PIXRF010 | [5 empty] | 2 |  | 6
3 |  |  |  | 0
Lisa | XREF_DSNAME1
|  | IH49037 | Y |  |  | LisaQ2 | Q2 | 2
|  | IH53002 | I |  |  |  |  | 2 |  |  |  |  | need function to check # in confirmation panel matches panel list #
|  | PIXRF005 | [5 empty] | 2
|  | PIXRF006 | [5 empty] | 2 |  | 8
4 |  |  |  | 0
Claudie | ADMINISTRATOR
|  | IC4B019 | [5 empty] | 4
|  | I10900 | Y |  |  | ClaudieQ2 | Q2 | 4
|  | ID14009 | Y |  |  | ClaudieQ1 | Q1 | 4
|  | IH11045 | Y |  |  | ClaudieQ2 | Q2 | 4
|  | IH12133 | Y |  |  | ClaudieQ1 | Q1 | 4
|  | IH25115 | Y |  |  | ClaudieQ1 | Q1 | 4
|  | IH3A033 | [5 empty] | 4 |  |  |  |  | obsolete password
|  | IH3A058 | Y |  |  | ClaudieQ2 | Q2 | 4
|  | IH4A016 | Y |  |  | ClaudieQ2 | Q2 | 4
|  | PIADM001 | Y |  |  | ClaudieQ2 | Q2 | 4
|  | PIADM002 | Y |  |  | ClaudieQ2 | Q2 | 4
|  | PIADM003 | Y |  |  | ClaudieQ2 | Q2 | 4 |  |  | 48
12 |  |  |  | 0
Claudie | XREF_JOB1
|  | IH4A042 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IC12012 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IC17008 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IC1B007 | [5 empty] | 2 |  |  |  |  | Obsolete pfkeys
|  | IC3A007 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | ID25004 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | ID25006 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | ID25007 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | ID25009 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | ID27005 | Y |  |  | ClaudieQ2 | Q2 | 2 |  |  | 20
10 |  |  |  | 0
Claudie | FOLDERS
|  | ASSIGN_FOLDER | Y |  |  | ClaudieQ2 | Q2
|  | IH12021 | Y |  |  | ClaudieQ2 | Q2
2 |  |  |  | 0
Claudie | MISC1
|  | I12511 | [5 empty] | 2
|  | I11316 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IC56006 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | ID17004 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH39023 | [5 empty] | 2
|  | IH43143 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH47053 | [5 empty] | 2
|  | IM85804 | Y |  |  | ClaudieQ2 | Q2 | 2 |  |  | 16
8 |  |  |  | 0
Claudie | PRINTSETUP
|  | IH1A122 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IC13015 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IC25010 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IC25011 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IC27007 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH12049 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH13053 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH17125 | [5 empty] | 2
|  | IH18079 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH49031 | Y |  |  | ClaudieQ2 | Q2 | 2 |  |  | 20
10 |  |  |  | 0
Claudie | SORTS
|  | IH1B052 | I |  |  | LisaQ2 | [6 empty] | need function for drop-down sort menu column compare
|  | IH36020 | [5 empty] | 2
|  | I725695 |  | Y |  | ClaudieQ2 | Q2
2 |  |  |  | 1
Claudie | XREF1 | [9 empty] | 2
|  | I13095 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | I13095a | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IC13001 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | I13034 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH1B022 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH45042 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IM104683 | Y |  |  | ClaudieQ2 | Q2 | 2 |  |  |  |  | Failed in PR290
|  | IM93881 | [5 empty] | 2
|  | IM90198 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | PIXRF001 | Y |  |  | ClaudieQ2 | Q2 | 2 |  |  | 20
10 |  |  |  | 0
Claudie | XREF_JOB2
|  | IH49035 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IC53007 | [5 empty] | 2 |  |  |  |  | Password specific
|  | IC53008 | [5 empty] | 2 |  |  |  |  | Password specific
|  | IC56005 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH28064 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH2B003 | [5 empty] | 2
|  | IH36050 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH39051 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH39100 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH3A064 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IU53024 | Y |  |  | ClaudieQ2 | Q2 | 2 |  |  | 24
11 |  |  |  | 0
Claudie | XREF_PGM1
|  | IC2B006 | [5 empty] | 2
|  | I12696 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IC2A003 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IC2C013 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH39098 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH49040 | [5 empty] | 2
|  | IM93874 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IM93932 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | PIXRF002 | Y |  |  | ClaudieQ2 | Q2 | 2 |  |  | 18
9 |  |  |  | 0
Claudie | XREF_PROC1
|  | ID25011 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH1A015 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH22161 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | IH44087 | Y |  |  | ClaudieQ2 | Q2 | 2
|  | PIXRF003 | Y |  |  | ClaudieQ2 | Q2 | 2 |  |  | 14
5 |  |  |  | 0
Claudie | XREF_SYSOUT1
|  | IH1A030 | [5 empty] | 2
|  | IH1A154 | [5 empty] | 2
|  | IM90333 | [5 empty] | 2
|  | PIXRF004 | [5 empty] | 2
4 |  |  |  | 0 |  |  |  | 2 |  |  | 10
| Total Est. Time (in hours) | [6 empty] | 384 | 0 | 192 | 192
| Total Est. Days | [6 empty] | 59.0769 | 0 | 29.5385 | 29.5385
| Total Number of Scripts | 175
| # of Scripts Converted | 74
| % Completed | 42.29%
| Total Number of New Scripts |  |  | 2
3 | Total for ClaudieQ1
62 | Total for ClaudieQ2
0 | Total for ClaudieQ3
0 | Total for ClaudieQ4
1 | Total for LisaQ1
11 | Total for LisaQ2
0 | Total for LisaQ3
0 | Total for LisaQ4
0 | Total for ScottQ1
0 | Total for ScottQ2
0 | Total for ScottQ3
0 | Total for ScottQ4

## Automation FY2010
Product | Version | Platform(s) | Type | Created by | # of TC as of 12/31/09 | # of TS as of 12/31/09 | # of TC as of 12/31/10 | # of TS as of 12/31/10 | New TC this FY | New TS this FY
Pro/JCL - ISPF | 2.9 | Z/OS | MAP | QA | 260 | 245 |  |  | 0 | 0
Info/Xe - ISPF | 2.9 | Z/OS | MAP | QA |  |  |  |  | 2 | 2
Info/Xe - Windows Client | 2.9 | W32; W64 | QTP | QA
|  |  |  | Totals | 260 | 245 | 0 | 0 | 2 | 2
|  |  |  | Increase | [5 empty] | #REF!
Notes:
Original 276 Pro/JCLTestCases were WinRunner; coverted to MAP scripts
Original 175 Info/Xe TestCases were WinRunner; coverted to MAP scripts

## Automation FY09
Product | Version | Platform(s) | Type | Created by | # of TC as of 12/31/09 | # of TS as of 12/31/09 | New TC this FY | New TS this FY
Pro/JCL - ISPF | 2.9 | Z/OS | MAP | QA | 260 | 245 | 4 | 248
Info/Xe - ISPF | 2.9 | Z/OS | MAP | QA
Info/Xe - Windows Client | 2.9 | W32; W64 | QTP | QA
|  |  |  | Totals | 260 | 245 | 4 | 248
|  |  |  | Increase |  |  |  | #REF!
Notes:
Original 276 Pro/JCLTestCases were WinRunner; coverted to MAP scripts
Original 175 Info/Xe TestCases were WinRunner; coverted to MAP scripts

## FY09 Totals
Quarter Totals
| Q1 |  | Q2 |  | Q3 |  | Q4 |  | FY TCtal
AuTCmation Type | TC | TS | TC | TS | TC | TS | TC | TS | TC | TS
MAP - Pro/JCL | [6 empty] | 260 | 245 | 260 | 245
MAP - Infox | [8 empty] | 0 | 0
[9 empty] | 0 | 0
TCtals | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 245 | 260 | 245
Totals for each AuTCmation Developer
| Q1 |  | Q2 |  | Q3 |  | Q4 |  | Developer TCtal
Developer | TC | TS | TC | TS | TC | TS | TC | TS | TC | TS
Claudie | [6 empty] | 260 | 248 | 260 | 248
Lisa | [8 empty] | 0 | 0
Scott | [8 empty] | 0 | 0
TCtals | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 248 | 260 | 248

## FY 2009 Coverage
Automation Type | Product | Area Covered | Owner | Test Cases | Scripts Q1 | Scripts Q2 | Scripts Q3 | Scripts Q4 | Total Scripts | % complt
MAP | Pro/JCL | Admin | Claudie | 7 |  |  |  |  | 6 | 85.7143
MAP | Pro/JCL | Help | Claudie | 14 |  |  |  |  | 14 | 100
MAP | Pro/JCL | JJ | Claudie | 50 |  |  |  |  | 49 | 98
MAP | Pro/JCL | JJDirect | Claudie | 15 |  |  |  |  | 13 | 86.6667
MAP | Pro/JCL | JJScan | Claudie | 3 |  |  |  |  | 3 | 100
MAP | Pro/JCL | JMP | Claudie | 0 |  |  |  |  | 17 | #DIV/0!
MAP | Pro/JCL | MISC | Claudie | 7 |  |  |  |  | 5 | 71.4286
MAP | Pro/JCL | Product Usage | Claudie | 1 |  |  |  |  | 0 | 0
MAP | Pro/JCL | Reformat | Claudie | 20 |  |  |  |  | 16 | 80
MAP | Pro/JCL | Remote Validation | Claudie | 8 |  |  |  |  | 8 | 100
MAP | Pro/JCL | RTS | Claudie | 47 |  |  |  |  | 40 | 85.1064
MAP | Pro/JCL | Scheduler | Claudie | 26 |  |  |  |  | 20 | 76.9231
MAP | Pro/JCL | Selection Exit | Claudie | 1 |  |  |  |  | 1 | 100
MAP | Pro/JCL | Selection List | Claudie | 7 |  |  |  |  | 6 | 85.7143
MAP | Pro/JCL | Shared | Claudie | 7 |  |  |  |  | 6 | 85.7143
MAP | Pro/JCL | STC | Claudie | 1 |  |  |  |  | 1 | 100
MAP | Pro/JCL | System | Claudie | 8 |  |  |  |  | 5 | 62.5
MAP | Pro/JCL | Validation | Claudie | 38 |  |  |  |  | 35 | 92.1053
QTP | Pro/JCL | Customize | Scott
QTP | Pro/JCL | JCL Editor | Scott
QTP | Pro/JCL | JMP | Scott
QTP | Pro/JCL | Local Scan | Scott
QTP | Pro/JCL | Mainframe Scan | Scott
QTP | Pro/JCL | Quick Scan | Scott
| Pro/JCL | Map Infrastructure/new functions | Scott
|  | Summary |  | 260 | 0 | 0 | 0 | 0 | 245 | 94.2308
MAP | INFOX |  | Scott
|  | Summary |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Automation |  | 260 | 0 | 0 | 0 | 0 | 245
Note: the Coverage-Detail report will be updated with a date routine to pull stats on a quarterly basis.