## FY10 Totals
Project Automation - FY 2010
| Test Cases |  | Q1 | Q2 | Q3 | Q4 | Total Scripts | % FY2010 Automation | Total Project Automation |  | Automation to Date
Automation Type | WinR | New TC | TS | TS | TS | TS | FY 2010 |  | TC | TS
MAP - Pro/JCL | 286 | 6 | 20 | 0 | 0 | 0 | 20 | 6.849% | 292 | 244 | 83.56%
MAP - Info/X | 183 | 8 | 6 | 87 | 64 | 5 | 162 | 84.82% | 191 | 170 | 89.01%
QTP - PJW | 46 | 0 | 0 | 0 | 6 | 0 | 6 | 13.04% | 46 | 6 | 13.04%
QTP - PIW | 48 | 16 | 3 | 27 | 0 | 0 | 30 | 46.88% | 64 | 46 | 71.88%
Totals | 563 | 14 | 26 | 87 | 70 | 5 | 218 | 36.76% | 593 | 466 | 78.58%
Totals for each Automation Developer for all of MGH products
| Test Cases |  | Q1 | Q2 | Q3 | Q4 | Total Scripts | % FY2010 Automation | Developer Totals |  | Automation by Developer
Developer | WinR | New TC | TS | TS | TS | TS | FY 2010 |  | TC | TS
Claudie | 563 |  | 29 | 69 | 60 | 0 | 158 | 28.06% | 563 | 158 | 28.06%
Lisa | 563 |  | 1 | 19 | 0 | 6 | 26 | 4.618% | 563 | 26 | 4.618%
Scott | 563 |  | 3 | 27 | 10 | 0 | 40 | 7.105% | 563 | 40 | 7.105%
Totals |  | 0 | 30 | 88 | 60 | 6 | 184 | 32.68% | 563 | 224 | 39.79%
Note* Percentages in column Automation to Date includes new scripts.

## Automation FY2010
Product | Version | Platform(s) | Type | Created by | # of TC as of 12/31/09 | # of TS as of 12/31/09 | # of TC as of 12/31/10 | # of TS as of 12/31/10 | New TC this FY | New TS this FY
Pro/JCL - ISPF | 3 | Z/OS | MAP | QA | 0 | 0 | 286 | 244 | 6 | 20
Info/X - ISPF | 3 | Z/OS | MAP | QA | 0 | 0 | 183 | 170 | 8 | 162
Pro/JCL - Windows Client | 3 | W32; W64 | QTP | QA | 0 | 0 | 46 | 6 | 0 | 6
Info/X- Windows Client | 3 | W32; W64 | QTP | QA | 0 | 0 | 48 | 46 | 16 | 30
|  |  |  | Increase |  |  |  |  | 30 | 218
Notes:
Original 276 Pro/JCLTestCases were WinRunner; converted to MAP scripts
Original 175 Info/Xe TestCases were WinRunner; converted to MAP scripts
PW: qamgh

## ProJCL-Coverage-2010
Automation Type | Product | Area Covered | Owner | WinRunner Cases | New Test Cases | Scripts Q1 | Scripts Q2 | Scripts Q3 | Scripts Q4 | Scripts FY10 | Total Scripts | % complt
MAP | Pro/JCL | Admin | Claudie | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 85.7143
MAP | Pro/JCL | Help | Claudie | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 100
MAP | Pro/JCL | JJ | Claudie | 52 | 2 | 1 | 0 | 0 | 0 | 1 | 50 | 96.1538
MAP | Pro/JCL | JJDirect | Claudie | 15 | 0 | 4 | 0 | 0 | 0 | 4 | 13 | 86.6667
MAP | Pro/JCL | JJScan | Claudie | 3 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | 100
MAP | Pro/JCL | JMP | Claudie | 17 | 0 | 2 | 0 | 0 | 0 | 2 | 17 | 100
MAP | Pro/JCL | MISC | Claudie | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 25
MAP | Pro/JCL | Product Usage | Claudie | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MAP | Pro/JCL | Reformat | Claudie | 20 | 1 | 1 | 0 | 0 | 0 | 1 | 16 | 80
MAP | Pro/JCL | Remote Validation | Claudie | 8 | 0 | 2 | 0 | 0 | 0 | 2 | 8 | 100
MAP | Pro/JCL | RTS | Claudie | 48 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 83.3333
MAP | Pro/JCL | Scheduler | Claudie | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 76.9231
MAP | Pro/JCL | Selection Exit | Claudie | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100
MAP | Pro/JCL | Selection List | Claudie | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 75
MAP | Pro/JCL | Shared | Claudie | 7 | 0 | 6 | 0 | 0 | 0 | 6 | 6 | 85.7143
MAP | Pro/JCL | STC | Claudie | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 100
MAP | Pro/JCL | System | Claudie | 8 | 0 | 1 | 0 | 0 | 0 | 1 | 5 | 62.5
MAP | Pro/JCL | Validation | Claudie | 38 | 0 | 1 | 0 | 0 | 0 | 1 | 35 | 92.1053
|  | Summary |  | 286 | 6 | 20 | 0 | 0 | 0 | 20 | 244
|  | Automation by Analyst | Claudie |  |  | 20 | 0 | 0 | 0 | 20 | 6.993%
|  |  | Lisa |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0!
|  |  | Scott |  |  | 0 | 0 | 0 | 0 | 0 | #DIV/0!

## Infox-Coverage-2010
Automation Type | Product | Area Covered | Owner | WinRunner Cases | New Test Cases | Scripts Q1 | Scripts Q2 | Scripts Q3 | Scripts Q4 | Scripts FY10 | Total Scripts | % complt
MAP | INFOX | A_NISSAN_263 | Lisa | 6 | 0 | 1 | 0 | 3 | 0 | 4 | 4 | 66.6667
| INFOX | QUERY1 | Lisa | 12 | 0 | 0 | 0 | 9 | 2 | 11 | 11 | 91.6667
| INFOX | REPORTS | Lisa | 22 | 1 | 0 | 0 | 17 | 1 | 18 | 18 | 81.8182
| INFOX | SETUP1 | Lisa | 22 | 2 | 0 | 6 | 11 | 0 | 17 | 17 | 77.2727
| INFOX | UPDATE1 | Lisa | 12 | 0 | 0 | 0 | 12 | 0 | 12 | 12 | 100
| INFOX | XREF_CICSGROUP1 | Lisa | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 50
| INFOX | XREF_CICSTRANSACTION1 | Lisa | 4 | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 100
| INFOX | XREF_DB2COLLECTIONID1 | Lisa | 3 | 1 | 0 | 3 | 0 | 0 | 3 | 3 | 100
| INFOX | XREF_DB2PACKAGE1 | Lisa | 3 | 0 | 0 | 2 | 1 | 0 | 3 | 3 | 100
| INFOX | XREF_DB2PLAN1 | Lisa | 2 | 0 | 0 | 1 | 1 | 0 | 2 | 2 | 100
| INFOX | XREF_DB2TABLE1 | Lisa | 3 | 0 | 0 | 2 | 1 | 0 | 3 | 3 | 100
| INFOX | XREF_DSNAME1 | Lisa | 4 | 0 | 0 | 2 | 2 | 0 | 4 | 4 | 100
| INFOX | ADMINISTRATOR | Claudie | 12 | 1 | 3 | 7 | 0 | 1 | 11 | 11 | 91.6667
| INFOX | XREF_JOB1 | Claudie | 10 | 0 | 2 | 9 | 0 | 1 | 12 | 12 | 120
| INFOX | FOLDERS | Claudie | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 2 | 100
| INFOX | MISC1 | Claudie | 8 | 1 | 0 | 6 | 0 | 0 | 6 | 6 | 75
| INFOX | PRINTSETUP | Claudie | 11 | 1 | 0 | 10 | 0 | 0 | 10 | 10 | 90.9091
| INFOX | SORTS | Claudie | 6 | 1 | 0 | 2 | 2 | 0 | 4 | 4 | 66.6667
| INFOX | XREF1 | Claudie | 10 | 0 | 0 | 9 | 0 | 0 | 9 | 9 | 90
| INFOX | XREF_JOB2 | Claudie | 11 | 0 | 0 | 9 | 0 | 0 | 9 | 9 | 81.8182
| INFOX | XREF_PGM1 | Claudie | 9 | 0 | 0 | 8 | 0 | 0 | 8 | 8 | 88.8889
| INFOX | XREF_PROC1 | Claudie | 5 | 0 | 0 | 5 | 0 | 0 | 5 | 5 | 100
| INFOX | XREF_SYSOUT1 | Claudie | 4 | 0 | 0 | 4 | 0 | 0 | 4 | 4 | 100
| INFOX | [8 empty] | 0
|  | Summary |  | 183 | 8 | 6 | 87 | 64 | 5 | 162 | 162
|  | Automation by Analyst | Claudie |  |  | 9 | 69 | 60 | 0 | 138 | 75.41%
|  |  | Lisa |  |  | 1 | 19 | 0 | 6 | 26 | 14.21%
|  |  | Scott |  |  | 0 | 0 | 4 | 0 | 4 | 2.186%
[6 empty] | 10 | 88 | 64 | 6 | 168 | 91.8%

## PIW-Detail-2010
Suite Totals | Suite | Suite | Converted to QTP Analsyt/Quarter | New Test Script (Y/N)? | Reqmt. Spec #/Comments
File Management
|  | file_manage_platform | scottq2 | y
|  | file_new | scottq2 | y
2 |  |  |  | 2
GUI Check
|  | GUIcheck_icon_fun | scottq1 | y
|  | GUIcheck_Tabs | scottq1 | y
|  | GUIcheck_XREF_Job_Contains | scottq2 | y
3 |  |  |  | 3
Help
|  | help_index2 | scottq2 | y
|  | help_index3 | scottq2 | y
|  | help_index4 |  |  | To be completed after 765936 has been fixed
|  | help_index5 |  |  | To be completed after 765936 has been fixed
|  | help_index6 |  |  | To be completed after 765936 has been fixed
|  | help_index7 |  |  | To be completed after 765936 has been fixed
|  | help_index8 |  |  | To be completed after 765936 has been fixed
|  | help_index9 |  |  | To be completed after 765936 has been fixed
|  | help_index10 |  |  | To be completed after 765936 has been fixed
|  | view_systemtabs | scottq2 | y
10 |  |  |  | 3
INFO/XE Cross Reference
|  | Data Sets |  |  | waiting TCD from Lisa
|  | Members |  |  | waiting TCD from Lisa
|  | Jobs |  |  | waiting TCD from Lisa
|  | Procs |  |  | waiting TCD from Lisa
|  | Execs |  |  | waiting TCD from Lisa
|  | Contains |  |  | waiting TCD from Lisa
|  | Sysouts |  |  | waiting TCD from Lisa
|  | DDNAME |  |  | waiting TCD from Lisa
|  | DDs |  |  | waiting TCD from Lisa
|  | DB2 Subsystem |  |  | waiting TCD from Lisa
|  | INFO/XE database |  |  | waiting TCD from Lisa
11 |  |  |  | 0
Impact Tickets
|  | CS11238 | scottq2
|  | CS13302 | scottq2 |  | need to figure out how to verify ballons on the right mouse clicks. Sent email to Genlogix
|  | CS13329 | scottq2
|  | CSC12005 | scottq2
|  | CSC14032 | scottq2
|  | CSD24012 | scottq1 | y
|  | CSH22159 | scottq2
|  | CSH25021 | scottq2
|  | CSH26053 | scottq2
|  | CSH41055 | scottq2
|  | CSH41056 | scottq2
|  | CSH41058 | scottq2
|  | CSH41085 | scottq2
|  | CSH48039 | scottq2
|  | I12560 | scottq2 |  | Balloon verifications needed
|  | PR91375 | scottq2 | y
|  | PR95535 | scottq2 | y
|  | PR95616 | scottq2 | y
|  | PR95734 | scottq2 | y
|  | PR95735 | scottq2 | y
|  | PR96709 | scottq2 | y
|  | PR97085 | scottq2 | y
22 |  |  |  | 8
Total Test Cases: |  | 48
| Total Number of Scripts | 48
| # of Scripts Converted | 22
| Total for all Quarters | 30
| % Completed | 62.5%
| Total Number of New Scripts | 9
| Analyst | Q1 |  | Q3 | Q4
| Claudie | 0 | 0 | 0 | 0
| Lisa | 0 | 0 | 0 | 0
| Scott | 3 | 27 | 0 | 0
| Totals | 3 | 27 | 0 | 0 | 30

## PIW-Coverage-2010
Automation Type | Product | Area Covered | Owner | WinRunner Cases | New Test Cases | Scripts Q1 | Scripts Q2 | Scripts Q3 | Scripts Q4 | Scripts FY11 | Total Scripts | % complt
MAP | INFOX | File Management | Scott | 2 | 2 | 0 | 2 | 0 | 0 | 2 | 2 | 100
| INFOX | GUI Check | Scott | 3 | 3 | 2 | 1 | 0 | 0 | 3 | 3 | 100
| INFOX | Help | Scott | 10 | 3 | 0 | 3 | 0 | 0 | 3 | 3 | 30
| INFOX | INFO/X Cross Reference | Scott | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| INFOX | Impact Tickets | Scott | 22 | 8 | 1 | 21 | 0 | 0 | 22 | 22 | 100
|  | Summary |  | 48 | 16 | 3 | 27 | 0 | 0 | 30 | 30
|  | Automation by Analyst | Claudie |  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | Lisa |  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | Scott |  |  | 3 | 27 | 0 | 0 | 30 | 62.5%
[6 empty] | 3 | 27 | 0 | 0 | 30 | 62.5%

## PJW-Coverage-2010
Automation Type | Product | Area Covered | Owner | WinRunner Cases | New Test Cases | Scripts Q1 | Scripts Q2 | Scripts Q3 | Scripts Q4 | Scripts FY10 | Total Scripts | % complt
MAP | INFOX | Customize | Scott | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 50
| INFOX | Basic Functionality | Scott | 6 | 0 | 0 | 0 | 5 | 0 | 5 | 5 | 83.3333
| INFOX | Impact Tickets | Scott | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Summary |  | 46 | 0 | 0 | 0 | 6 | 0 | 6 | 6
|  | Automation by Analyst | Claudie |  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | Lisa |  |  | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | Scott |  |  | 0 | 0 | 6 | 0 | 6 | 13.04%
[6 empty] | 0 | 0 | 6 | 0 | 6 | 13.04%

## ProJcl-Detail-2010
|  |  | Converted | New | [5 empty] | Code | Script
Total for Suite |  | WinRunner Scripts | to MAP | Script | Date | Analyst | Quarter 2010 | Analyst/Qtr | Comments | Review | P/F/I | Date | Analyst | Notes
ADMIN1:
|  | PD1B006 | X |  | 2009-01-09 | LisaC
|  | PH35055 |  |  | 2009-02-02 | LisaC |  |  | need function to handle parameter tables
|  | PH43055 | X |  | 2009-08-21 | cjm |  |  | need function to check cursor position
|  | PH15034 | X |  | 2009-08-19 | LisaC |  |  | waiting for 'presskey' function & function to handle popup panel w/ no scroll field
|  | PH49014 | X |  | 2009-08-20 | cjm
|  | PH48002 | X |  | 2009-08-21 | cjm
|  | PH16071 | X |  | 2009-08-24 | cjm
7 |  |  |  | 0
HELP1:
|  | HELP_ADMINISTRATION | X |  | 2009-05-04 | cjm |  |  | D0JHDIA3.txt has 2 panel ID (the first panel and the superimposed popup panelid)
|  | HELP_JMP_SETTINGS | X |  | 2009-08-24 | cjm
|  | HELP_MAINMENU | X |  | 2009-05-05 | cjm
|  | HELP_REFORMATTER | X |  | 2009-05-20 | cjm
|  | HELP_REFORMATTER_STATEMENTS | X |  | 2009-05-20 | cjm
|  | HELP_RTS_SETTINGS | X |  | 2009-05-05 | cjm
6
HELP2:
|  | P12738 | X |  | 2009-05-28 | cjm
|  | P13219 | X |  | 2009-05-28 | cjm
|  | PC11012 | X |  | 2009-05-28 | cjm |  |  | capture Reformat DD help panel D0SHREF3 has extra blank pages at the bottom.
|  | PH22125 | X |  | 2009-06-01 | cjm
|  | PH25112 | X |  | 2009-06-01 | cjm
|  | PH2C051 | X |  | 2009-06-01 | cjm
|  | PH43053 | X |  | 2009-06-02 | cjm |  |  | Test for copyright failed opening Impact ticket: 683536
|  | P685586 | X |  | 2009-11-09 | cjm |  |  | New testcase PR290
8 |  |  |  | 0
JJ1
|  | P10927 | X |  | 2009-02-26 | cjm
|  | P11135 | X |  | 2009-01-29 | LisaC
|  | P11573 | X |  | 2009-02-25 | cjm
|  | P12455 | X |  | 2009-02-25 | cjm
|  | P12479 | X |  | 2009-02-26 | cjm
|  | P12783 | X |  | 2009-02-25 | cjm
|  | P13394 | X |  | 2009-12-02 | cjm
|  | PC24008 | X |  | 2009-02-27 | cjm
|  | PH11081 | X |  | 2009-12-03 | cjm
|  | PH11083 | X |  | 2009-02-27 | cjm
|  | PH12020 | X |  | 2009-02-24 | cjm
|  | PH22137 | X |  | 2009-02-24 | cjm
|  | PH28151 | X |  | 2009-09-23 | cjm |  |  | need to check direct execution jmp messages/added p106089
|  | PH29030 | X |  | 2009-02-26 | cjm
|  | PH29034 | X |  | 2009-02-25 | cjm
|  | PH2A021 | X |  | 2009-02-25 | cjm
|  | PC1A018 | X |  | 2009-03-02 | cjm
|  | PR13295 | X |  | 2009-02-24 | cjm
18
JJ2
|  | P665386 | X |  | 2009-11-16 | cjm |  |  | new script added on PR290
|  | P722146 | X | y | 2010-10-18 | Cjm
|  | PC38013 | X |  | 2009-02-21 | cjm
|  | PC5B001 | [6 empty] | Checking for a B37 (may take too long to run).
|  | PH21085 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH35063 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PR10126 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PR12783 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PR12988 | X |  | 2009-02-24 | cjm |  |  |  | skb
|  | PR13084 | X |  | 2009-02-03 | cjm |  |  |  | skb
|  | PR13123 | X |  | 2009-03-02 | cjm |  |  | use verifyPopup. COMPLETED/ Needs review
|  | PR13225 | X |  | 2009-02-05 | cjm |  |  |  | skb
|  | PR13272 | X |  | 2009-02-09 | cjm |  |  |  | skb
|  | PR13398 | X |  | 2009-02-10 | cjm |  |  |  | skb
|  | PC1C002 | X |  | 2009-02-11 | cjm |  |  |  | skb
|  | PU16004 | X |  | 2009-02-11 | cjm |  |  |  | skb
|  | PU1C007 | X |  | 2009-02-11 | cjm |  |  |  | skb
|  | PC38001 | X |  | 2/24.2009 | cjm |  |  | This script needs to run TZ17A because of Migrated dataset. | skb
|  | PH3C024 | X |  | 2009-02-12 | cjm |  |  |  | skb
|  | PC3B013 | X |  | 2009-02-19 | cjm |  |  |  | skb
|  | PH39099 | X |  | 2009-02-20 | cjm |  |  |  | skb
|  | PH43180 | X |  | 2009-02-20 | cjm |  |  |  | skb
|  | PH42017 | X |  | 2009-02-20 | cjm |  |  |  | skb
|  | PH43112 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH43054 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH3A067 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH42016 | X |  | 2010-01-27 | cjm | Q1 | ClaudieQ1
|  | PH3A015 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH3A059 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH3A062 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH3A065 | X |  | 2009-02-23 | cjm |  |  |  | skb
|  | PH3A114 | X |  | 2009-02-24 | cjm |  |  |  | skb
|  | PH49013 | X |  | 2009-02-24 | cjm |  |  |  | skb
|  | PR715672 | X | Y | 2010-11-15 | cjm |  | PR300
34 |  |  |  | 2
JJDIRECT1
|  | PH28086 | X |  | 2010-01-28 | cjm | Q1 | ClaudieQ1
|  | PH29103 | X |  | 2009-09-02 | cjm
|  | PH34042 | I |  | 2010-01-27 | cjm
|  | PD29007 | X |  | 2009-06-30 | cjm
|  | PH2A147 | X |  | 2009-07-01 | cjm
|  | PH2A157 | X |  | 2009-07-06 | cjm
|  | PH3A115 | X |  | 2009-07-07 | cjm
|  | PD28006 | X |  | 2010-01-28 | cjm | Q1 | ClaudieQ1 | when capturing report bottom of data does not show up .
|  | PH44080 | X |  | 2009-06-29 | cjm
|  | PH4C001 | X |  | 2009-06-29 | cjm
|  | PU4B014 | X |  | 2009-07-01 | cjm
PU42008
|  | PH43016 | X |  | 2010-02-25 | cjm | Q1 | ClaudieQ1
|  | PH48003 | X |  | 2010-03-08 | cjm | Q1 | ClaudieQ1
|  | PH48030 | X |  | 2009-06-24 | cjm
15 |  |  |  | 0
JJSCAN1:
|  | PC26009 | X |  | 2010-03-08 | cjm | Q1 | ClaudieQ1 | Need to capture SJL DNS
|  | PH11087 | X |  | 2009-07-08 | cjm
|  | PR13125 | X |  | 3/2/20009 | cjm
3 |  |  |  | 0
JMP1:
|  | PH12043 | X |  | 2009-06-10 | cjm
|  | PH24088 | X |  | 2009-06-10 | cm
|  | PH26061 | X |  | 2009-06-10 | cjm
|  | PH27044 | X |  | 2009-06-11 | cjm
|  | PR12540 | X |  | 2009-06-11 | cjm
|  | PH35015 | X |  | 2009-06-11 | cjm
|  | PH39104 | X |  | 2009-06-11 | cjm
|  | SR11048 | X |  | 2010-03-08 | cjm | Q1 | ClaudieQ1
|  | PH21117 | X |  | 6/15.2009 | cjm |  |  | Need Model panel to be installed
|  | PH27059 | X |  | 2010-03-02 | cjm | Q1 | ClaudieQ1
|  | PU14008 | X |  | 2009-06-11 | cjm
|  | PC35004 | x |  | 2010-03-04 | cjm
|  | PU4B007 | X |  | 2009-06-15 | cjm
|  | PH37022 | X |  | 2009-06-11 | cjm
|  | PH42110 | X |  | 2009-06-11 | cjm
|  | PH51010 | X |  | 2009-06-15 | cjm
|  | P662041 | X |  | 2009-10-15 | cjm |  |  | PR290 new script
17 |  |  |  | 0
MISC1:
|  | PR12492 | X |  | 2009-04-29 | cjm
|  | PR661065 | X | y | 2010-11-04 | cjm
|  | PU29009 | X |  | 2009-06-02 | skb
|  | PH41001 | X |  | 2009-04-28 | cjm
|  | PH35040 | X |  | 2009-05-27 | cjm |  |  | fixed by skb
|  | PC2A010 | X |  | 2009-04-27 | cjm |  |  | fixed by skb Multiple field with the same name on form
|  | PH41037 | [6 empty] | Need to have libraries allocated for one release and calling a different release
|  | PH13056 | X |  | 2009-04-30 | cjm
|  | PU4A010 | X |  | 2009-04-27 | cjm
PH31025
|  | P687454 | X |  | 2009-11-19 | cjm
|  | PR742531 | X | y | 2010-11-22 | cjm
12 |  |  |  | 1
PRODUCT USAGE:
PH45030
1 |  |  |  | 0
REFORMAT1:
|  | P707881 | X | y | 2010-10-18 | cjm
|  | PH25013 | X |  | 2009-06-04 | skb
|  | P11706 | X |  | 2010-03-04 | cjm | Q1 | ClaudieQ1
|  | PC25013 | X |  | 6/23/20009 | cjm
|  | PH12015 | X |  | 2009-06-24 | cjm
PH13023
|  | PR10495 | X |  | 2009-06-24 | cjm
|  | PR10516 | X |  | 2009-06-23 | cjm
|  | PC25015 | X |  | 2009-06-23 | cjm
|  | PT0262 | X |  | 2009-06-22 | cjm |  |  | need to check why enable reformat does not stay to N for If statement
|  | PH43124 | X |  | 2009-06-18 | cjm
|  | PH3A082 | [6 empty] | ISPF statistics
|  | PH33064 | [6 empty] | Loop to work on reformat
|  | P10715 | X |  | 2009-06-18 | cjm
|  | P100109 | X |  | 2009-06-18 | cjm
|  | PH12083 | X |  | 2009-06-16 | cjm
|  | PH41079 | X |  | 2009-06-16 | cjm
PH4C029
|  | PH56048 | X |  | 2009-06-16 | cjm
|  | PH57007 | X |  | 2009-06-15 | cjm
|  | P103451 | X |  | 2009-09-23 | cjm |  |  | new script for 290
20 |  |  |  | 1
REMOTE_VALIDATION1:
|  | P571146 | X |  | 2010-01-07 | cjm | Q1 | ClaudieQ1 | new script for 290
|  | PH43167 | X |  | 2009-07-25 | cjm |  |  | Need to remove the "forced enter" on panelListAction function to capture a Help Screen for Direct execution Select help panel..
|  | PH43023 | X |  | 2009-09-02 | cjm
|  | PH43018 | X |  | 2009-09-02 | cjm
|  | PH43091 | X |  | 2009-09-03 | cjm
|  | PH43097 | X |  | 2009-09-03 | cjm
|  | PH43027 | X |  | 2009-09-03 | cjm
|  | PR98118 | X |  | 2010-01-12 | cjm | Q1 | ClaudieQ1 | new script for 290
8 |  |  |  | 0
RTS1:
|  | P106892 | X |  | 2009-09-22 | cjm
|  | P100103 | X |  | 2009-04-28 | cjm
|  | P10883 | X |  | 2009-04-08 | cjm |  |  | Problem capture help popup / Fixed
|  | P12534 | X |  | 2009-04-14 | cjm
|  | P12671 | X |  | 2009-04-15 | cjm
|  | P12834 | X |  | 2009-04-15 | cjm
|  | PC12001 | X |  | 2009-04-15 | cjm
|  | PC21002 | [6 empty] | RMM
|  | PC22012 | X |  | 2009-04-16 | cjm
|  | PC27005 | X |  | 2009-04-16 | cjm
|  | PH12036 | X |  | 2009-04-16 | cjm
|  | PH12038 | X |  | 2009-04-28 | cjm
|  | PH16232 | X |  | 2009-04-20 | cjm
|  | PH18111 | X |  | 2009-04-20 | cjm
|  | PH22121 | X |  | 2009-04-20 | cjm
|  | PH24015 | X |  | 2009-12-02 | cjm
|  | PH25062 | X |  | 2009-04-20 | cjm
|  | PH25072 | X |  | 2009-04-20 | cjm
|  | PR10478 | X |  | 2009-12-01 | cjm
SH36067
20
RTS2:
|  | P11135 | X |  | 2009-04-21 | cjm
|  | P11316 | X |  | 2009-12-01 | cjm
|  | P13292 | X |  | 2009-04-22 | cjm
|  | PC15006 | X |  | 2009-03-24 | cjm
|  | PC26004 | X |  | 2009-03-30 | cjm
|  | PC2C003 | X |  | 2009-03-30 | cjm
PC38009
|  | PC48006 | X |  | 2009-03-31 | cjm
PC48008
|  | PC53004 | X |  | 2009-04-22 | cjm
|  | PH12124 | X |  | 2009-03-31 | cjm
|  | PH24013 | X |  | 2009-06-02 | cjm
|  | PH25019 | X |  | 2009-03-31 | cjm
PH2A130
|  | PH32016 | X |  | 2009-04-01 | cjm
|  | PH42014 | X |  | 2009-04-01 | cjm |  |  | Problems capturing help panels from popup list panel Fixed
|  | PH42059 | X |  | 2009-04-01 | cjm |  |  | blank popup panel for JCL Printing
|  | PH49001 | X |  | 2009-06-03 | skb |  |  | Looking for rts win280 and not found
|  | PR11136 | X |  | 2009-04-02 | cjm
|  | PR11382 | X |  | 2009-06-04 | skb |  |  | unable to find string on child popup
|  | PR11489 | X |  | 2009-06-04 | LisaC/skb
|  | PR11624 | X |  | 2009-04-06 | cjm |  |  | capture entire output byrun byjob…..
|  | PR11948 | X |  | 2009-04-06 | cjm
PR13170
|  | PT0970 | X |  | 2009-04-07 | cjm
|  | PU3A002 | X |  | 2009-04-07 | cjm |  |  | another strange popup within popup capture on Library type Add option
S10077
|  | PR734545 | X | y | 2010-11-15 | cjm |  |  | New Scrip PR300
28 |  |  |  | 1
SCHEDULER1:
|  | P653071 | X |  | 2009-09-23 | cjm |  |  | New Script for 290
|  | P13378 | X |  | 2009-09-03 | cjm
|  | PC28002 | X |  | 2009-09-04 | cjm
|  | PH12007 | X |  | 2009-09-04 | cjm |  |  | Verify popup: duplicate last line of Scheduler Popup
|  | PH14059 | X |  | 2009-09-04 | cjm
|  | PH15025 | X |  | 2009-09-09 | cjm |  |  | need to check if TWS8 is up or down
|  | PH21078 | X |  | 2009-09-16 | cjm
PH2A019
|  | PH33045 | X |  | 2009-09-10 | cjm
|  | PH27003 | X |  | 2009-09-04 | cjm
|  | PH32040 | X |  | 2009-09-16 | cjm
PH23054
PH43035
PH3C059
|  | PH34010 | X |  | 2009-09-10 | cjm
|  | PC4A009 | X |  | 2009-09-14 | cjm
|  | P13192 | X |  | 2009-09-14 | cjm
|  | PH15031 | X |  | 2009-09-10 | cjm
|  | PH58032 | X |  | 2009-09-11 | cjm
|  | PH59003 | X |  | 2009-09-11 | cjm
|  | PH64037 | X |  | 2009-09-16 | cjm
|  | PU56005 | X |  | 2009-09-11 | cjm
|  | P11005 | X |  | 2009-09-11 | cjm
|  | PH12118 | X |  | 2009-09-11 | cjm
PC34009
PH15024
26 |  |  |  | 0
SELECTIONEXIT1:
|  | PC31010 | X |  | 2009-06-09 | cjm
1 |  |  |  | 0
SELECTIONLIST1:
|  | PH13031 | X |  | 2009-06-03 | cjm
PH26055
|  | PH2A145 | X |  | 2009-06-04 | cjm
|  | PH2B103 | X |  | 2009-06-04 | cjm
|  | PH27018 | X |  | 2009-06-08 | cjm
|  | PH33092 | X |  | 2009-06-08 | cjm
|  | PH39096 | X |  | 2009-06-09 | cjm
|  | p704399 | X | y | 2010-10-20 | cjm
8 |  |  |  | 1
SHARED1
SH2B075
|  | SH1B067 | X |  | 2010-03-15 | cjm | q1 | ClaudieQ1
|  | SR10763 | X |  | 2010-03-16 | cjm | q1 | ClaudieQ1
|  | SH42022 | X |  | 2010-03-16 | cjm | q1 | ClaudieQ1
|  | SH3A096 | X |  | 2010-03-06 | cjm | q1 | ClaudieQ1 | popup panel is icomplete when only 1 panel and no scroll
|  | SH22158 | X |  | 2010-03-17 | cjm | q1 | ClaudieQ1
|  | SH32085 | X |  | 2010-03-17 | cjm | q1 | ClaudieQ1
7 |  |  |  | 0
STC1:
|  | PH25064 | X |  | 2010-03-03 | cjm | q1 | ClaudieQ1
1 |  |  |  | 0
SYSTEM1:
|  | P11786 | X |  | 2009-06-02 | cjm
|  | P12340 | X |  | 2009-06-02 | cjm
|  | P13357 | X |  | 2010-02-18 | cjm | q1 | ClaudieQ1
|  | PH2A146 | X |  | 2009-06-03 | cjm
|  | PH32071 | X |  | 2009-06-03 | cjm
PH39003
|  | PH43024 | [6 empty] | Need a Master and Slave up for this script
|  | PH21176 | [6 empty] | Product usage
8 |  |  |  | 0
VALIDATION1:
|  | P13028 | X |  | 2009-03-16 | cjm
|  | PH11044 | X |  | 2009-03-16 | cjm
|  | PH12062 | [6 empty] | Loop on mem list
|  | PH12091 | X |  | 2009-03-16 | cjm
|  | PH21106 | X |  | 2009-03-16 | cjm
|  | PH28049 | X |  | 2009-03-18 | cjm
|  | PH2A113 | X |  | 2009-03-16 | cjm
|  | PH2A126 | X |  | 2009-06-02 | skb |  |  | not able to capture the entire help panel. Line 73 in script
|  | PH2A155 | X |  | 2009-03-17 | cjm
|  | PH2B029 | X |  | 2009-06-02 | skb |  |  | Added the ln $status to script. Update before working on it to get updates from repo
|  | PH31032 | X |  | 2009-03-17 | cjm
|  | PH36040 | X |  | 2009-03-17 | cjm
|  | PR100036 | X |  | 2009-04-21 | cjm |  |  | Would need toe rerun (capture Option Report / Missing popup title)
|  | PR10551 | X |  | 2009-03-19 | cjm |  |  | You must have rts member pjgl0020 for this test to run.
|  | PH47009 | X |  | 2009-07-09 | cjm
|  | PH43104 | X |  | 2009-04-22 | cjm |  |  | TESTING PCFILE RESTORE AFTER ADDING A MACHINE DEFINITION
|  | PH44019 | X |  | 2009-03-17 | cjm
17 |  |  |  | 0
VALIDATION2:
|  | PR11725 | X |  | 2009-03-02 | cjm
|  | PR12777 | X |  | 2009-03-02 | cjm
|  | PR13147 | X |  | 2009-03-02 | cjm
|  | PT1279 | X |  | 2009-03-03 | cjm
|  | PC2C004 | X |  | 2009-03-13 | cjm
|  | PU1A002 | X |  | 2009-03-04 | cjm
PH13009
|  | PH3A112 | X |  | 2009-03-13 | cjm
|  | PH33049 | X |  | 2010-02-18 | cjm | q1 | ClaudieQ1
|  | PH59059 | X |  | 2009-03-24 | cjm
|  | PH24071 | X |  | 2009-03-05 | cjm |  |  | Added pcfile reset
|  | PR10169 | X |  | 2009-03-05 | cjm |  |  | Problem capturing screen messages/fixed by capturing SJL instead. | Fixed/Modified to MAP- messages during busy not supported in MAP.
|  | PH42031 | X |  | 2009-03-10 | cjm
|  | PH42007 | [6 empty] | OPC
|  | PH24068 | X |  | 2009-03-10 | cjm
|  | PH43129 | X |  | 2009-03-11 | cjm
|  | P12144 | X |  | 2009-03-16 | cjm
|  | P11999 | X |  | 2009-03-11 | cjm
|  | PC31015 | X |  | 2009-04-21 | cjm
|  | PH31113 | X |  | 2009-03-11 | cjm
|  | PH38049 | X |  | 2009-03-23 | cjm |  |  |  | Fixed/ Script still needs to be finished. | F | 2009-03-20 | skb
21 |  |  |  | 0
|  | Total number of scripts to convert | 286
|  | # of scripts converted to date | 255
|  | % complete | 89.16%
|  | # Of New Scritps | 7
|  | Remaining Scripts | 31
| Scripts by Quarter/Analyst | Q1 | Q2 | Q3 | Q4
| Claudie | 20 | 0 | 0 | 0
| Lisa | 0 | 0 | 0 | 0
| Scott | 0 | 0 | 0 | 0
| Totals | 20 | 0 | 0 | 0 |  | 20

## Infox-Detail-2011
Suite Totals | Suite | Test Case Document | Converted to MAP | New Scripts | Date | Analyst/Qtr | Comments | Comments
Lisa | A_NISSAN_263
|  | IC53007 | Y |  |  | LisaQ1
|  | IH54039 | Y |  |  | ClaudieQ3 | scott | Ticket 741530
IC55006
|  | IC55006 | N/A |  |  |  |  | Password panel
|  | IC55010 | Y |  |  | ClaudieQ3
|  | IH54029 | Y |  |  | ClaudieQ3
6 |  |  |  | 0
Lisa | QUERY1
|  | IH4B026 | Y |  |  | LisaQ4 |  | Script fails for ticket 742896 in PR290
|  | I12602 | Y |  |  | ClaudieQ3
|  | I12628 | Y |  |  | ClaudieQ3
|  | I12757 | Y |  |  | scottQ3
|  | I724237 |  |  |  | LisaQ4 |  | new script for PR300
|  | IH11020 | Y |  |  | scottQ3
|  | IH1A166 | Y |  |  | scottQ3
|  | IH55035 | y |  |  | scottQ3
|  | IU3A008 | Y |  |  | ClaudieQ3
|  | IM92355 | Y |  |  | ClaudieQ3
|  | PIQRY001 | Y |  |  | ClaudieQ3
|  | IX645799 |  | Y |  | ClaudieQ1 |  | PR300 - 2011
12
Lisa | REPORTS |  |  | 1
|  | IH54031 | in progress |  |  | Lisa |  | Need to create a popup dropdown list routine
|  | IC11025 | Y |  |  | LisaQ4
|  | IC18007 | Y |  |  | ClaudieQ3
|  | IC1C005 | Y |  |  | ClaudieQ3
|  | IC27001 | Y |  |  | ClaudieQ3
|  | ID12008 | Y |  |  | ClaudieQ3
|  | ID12010 | Y |  |  | ClaudieQ3
|  | IH12106 | Y |  |  | ClaudieQ3
|  | IH1C035 | Y |  |  | ClaudieQ3
|  | IH1C071 | Y |  |  | ClaudieQ3
|  | IH23036 | Y |  |  | ClaudieQ3
|  | IH48061 | Y |  |  | ClaudieQ3 |  | merge h48031 with h48061
|  | IH48075 | Y |  |  | ClaudieQ3 |  | Lisa 11/12/10: updated script for tickets #711140 and #711131 fixed in PR300.
IH49074
|  | IH4B045 | Y |  |  | ClaudieQ3
|  | IH52016 | in progress |  |  | Lisa
|  | IH54012 | Y |  |  | ClaudieQ3
|  | IH55012 | Y |  |  | ClaudieQ3
|  | IH55054 | Y |  |  | ClaudieQ3
|  | IM92493 | Y |  |  | ClaudieQ3 |  | XREF is taking a long time with wild card
|  | IM92538 | Y |  |  | ClaudieQ3
|  | IX739812 |  | Y |  | ClaudieQ1 |  | PR300 - 2011
22 |  |  |  | 1
Lisa | SETUP1
|  | I704136 | C |  |  | LisaQ4
|  | IH48072 | Y |  |  | LisaQ2
|  | IC1B003 | Y |  |  | LisaQ2
|  | IH12135 | Y |  |  | LisaQ2
|  | IH13027 | Y |  |  | ClaudieQ3
IH16065
|  | IH1A097 | Y |  |  | LisaQ2
|  | IH35079 | Y |  |  | LisaQ2
|  | IH3B034 | Y |  |  | LisaQ2
|  | IH46012 | on hold
|  | IH48060 | Y |  |  | ClaudieQ3
|  | IH49009 | Y |  |  | ClaudieQ3
|  | IH4A031 | Y |  |  | ClaudieQ3
|  | IH4A047 | Y |  |  | ClaudieQ3
|  | IH4B007 | Y |  |  | ClaudieQ3
|  | IH4C014 | Y |  |  | ClaudieQ3
|  | IH52034 | Y |  |  | ClaudieQ3
|  | IM92078 | Y |  |  | ClaudieQ3
|  | IM108845 | Y |  |  | ClaudieQ3
|  | P695135 | Y |  |  | ClaudieQ3
|  | IX704140 |  | Y |  | ClaudieQ1 |  | PR300 - 2011
|  | IX717963 |  | Y |  | ClaudieQ1 |  | PR300 - 2011
22 |  |  |  | 2
Lisa | UPDATE1
|  | IH54062 | Y |  |  | ClaudieQ3
|  | I11903 | Y |  |  | ClaudieQ3
|  | IC1A023 | Y |  |  | ClaudieQ3
|  | IH12176 | Y |  |  | ClaudieQ3
|  | IH12235 | Y |  |  | ClaudieQ3
|  | IH16064 | Y |  |  | ClaudieQ3
|  | IH16151 | Y |  |  | ClaudieQ3
|  | IH21101 | Y |  |  | ClaudieQ3
|  | IH25016 | Y |  |  | ClaudieQ3
|  | IH25036 | Y |  |  | ClaudieQ3
|  | IH3A127 | Y |  |  | ClaudieQ3
|  | IH3C036 | Y |  |  | ClaudieQ3
12 |  |  |  | 0
Lisa | XREF_CICSGROUP1
|  | IH36024 | Y |  |  | ClaudieQ3
IH46042
2 |  |  |  | 0
Lisa | XREF_CICSTRANSACTION1
|  | IH1A028 | Y |  |  | ClaudieQ3
|  | IH35045 | Y |  |  | ClaudieQ3
|  | IH39102 | Y |  |  | ClaudieQ3
|  | IM91489 | Y |  |  | ClaudieQ3
4 |  |  |  | 0
Lisa | XREF_DB2COLLECTIONID1
|  | IM92010 | Y |  |  | LisaQ2
|  | PIXRF008 | Y |  |  | LisaQ2
|  | PI106569 | Y | Y |  | LisaQ2
3 |  |  |  | 1 |  | LisaQ2
Lisa | XREF_DB2PACKAGE1
|  | IH13043 | Y |  |  | LisaQ2
|  | IH12046 | Y |  |  | LisaQ2
|  | PIXRF009 | Y |  |  | ClaudieQ3
3 |  |  |  | 0
Lisa | XREF_DB2PLAN1
|  | IM91549 | Y |  |  | LisaQ2
|  | PIXRF007 | Y |  |  | ClaudieQ3
2 |  |  |  | 0
Lisa | XREF_DB2TABLE1
|  | ID25008 | Y |  |  | LisaQ2
|  | IM90400 | Y |  |  | LisaQ2
|  | PIXRF010 | Y |  |  | ClaudieQ3
3 |  |  |  | 0
Lisa | XREF_DSNAME1
|  | IH49037 | Y |  |  | LisaQ2
|  | IH53002 | Y |  |  | LisaQ2 |  | need function to check # in confirmation panel matches panel list #
|  | PIXRF005 | Y |  |  | ClaudieQ3
|  | PIXRF006 | Y |  |  | ClaudieQ3
4 |  |  |  | 0
Claudie | ADMINISTRATOR
|  | IC4B019 | [5 empty] | installation script
|  | I715736 |  | Y |  | LisaQ4
|  | I10900 | Y |  |  | ClaudieQ2
|  | ID14009 | Y |  |  | ClaudieQ1
|  | IH11045 | Y |  |  | ClaudieQ2
|  | IH12133 | Y |  |  | ClaudieQ1
|  | IH25115 | Y |  |  | ClaudieQ1
|  | IH3A058 | Y |  |  | ClaudieQ2
|  | IH4A016 | Y |  |  | ClaudieQ2
|  | PIADM001 | Y |  |  | ClaudieQ2
|  | PIADM002 | Y |  |  | ClaudieQ2
|  | PIADM003 | Y |  |  | ClaudieQ2
12 |  |  |  | 1
Claudie | XREF_JOB1
|  | IH4A042 | Y |  |  | ClaudieQ2
|  | IC12012 | Y |  |  | ClaudieQ2
|  | IC17008 | Y |  |  | ClaudieQ2
|  | IC3A007 | Y |  |  | ClaudieQ2
|  | IC3A008 | Y | 1 |  | LisaQ4
|  | ID25004 | Y |  |  | ClaudieQ2
|  | ID25006 | Y |  |  | ClaudieQ2
|  | ID25007 | Y |  |  | ClaudieQ2
|  | ID25009 | Y |  |  | ClaudieQ2
|  | ID27005 | Y |  |  | ClaudieQ2
10 |  |  |  | 0
Claudie | FOLDERS
|  | ASSIGN_FOLDER | Y |  |  | ClaudieQ2
|  | IH12021 | Y |  |  | ClaudieQ2
2 |  |  |  | 0
Claudie | MISC1
I12511
|  | I11316 | Y |  |  | ClaudieQ2
|  | IC56006 | Y |  |  | ClaudieQ2
|  | ID17004 | Y |  |  | ClaudieQ2
|  | IH39023 | Y |  |  | ClaudieQ2
|  | IH43143 | Y |  |  | ClaudieQ2
IH47053
|  | IM85804 | Y |  |  | ClaudieQ2
|  | PR715215 | Y | Y |  | ClaudieQ4
8 |  |  |  | 1
Claudie | PRINTSETUP
|  | IH1A122 | Y |  |  | ClaudieQ2
|  | IC13015 | Y |  |  | ClaudieQ2
|  | IC25010 | Y |  |  | ClaudieQ2
|  | IC25011 | Y |  |  | ClaudieQ2
|  | IC27007 | Y |  |  | ClaudieQ2
|  | IH12049 | Y |  |  | ClaudieQ2
|  | IH13053 | Y |  |  | ClaudieQ2
|  | IH17125 | Y |  |  | ClaudieQ2
|  | IH18079 | Y |  |  | ClaudieQ2
|  | IH49031 | Y |  |  | ClaudieQ2
|  | IX742336 |  | Y |  | ClaudieQ1 |  | PR300 - 2011
11 |  |  |  | 1
Claudie | SORTS
|  | IH1B052 | Y |  |  | LisaQ2 |  | Infox::verifySortedColumnData function needs updates; Script fails in PR290
|  | IH1C005 | Y | todo new |  | LisaQ2 |  | Script fails in PR290.
IH1B047
|  | IH36020 | Y |  |  | ClaudieQ3
|  | I725695 | Y |  |  | ClaudieQ3
|  | IX730455 |  | Y |  | ClaudieQ1 |  | PR300 - 2011
6 |  |  |  | 1
Claudie | XREF1
|  | I13095 | Y |  |  | ClaudieQ2
|  | I13095a | Y |  |  | ClaudieQ2
|  | IC13001 | Y |  |  | ClaudieQ2
|  | I13034 | Y |  |  | ClaudieQ2
|  | IH1B022 | Y |  |  | ClaudieQ2
|  | IH45042 | Y |  |  | ClaudieQ2
|  | IM104683 | Y |  |  | ClaudieQ2 |  | Failed in PR290
IM93881
|  | IM90198 | Y |  |  | ClaudieQ2
|  | PIXRF001 | Y |  |  | ClaudieQ2
10 |  |  |  | 0
Claudie | XREF_JOB2
| 11 | IH49035 | Y |  |  | ClaudieQ2
|  | IC53007 | [5 empty] | Password specific
|  | IC53008 | [5 empty] | Password specific
|  | IC56005 | Y |  |  | ClaudieQ2
|  | IH28064 | Y |  |  | ClaudieQ2
|  | IH2B003 | Y |  |  | ClaudieQ2
|  | IH36050 | Y |  |  | ClaudieQ2
|  | IH39051 | Y |  |  | ClaudieQ2
|  | IH39100 | Y |  |  | ClaudieQ2
|  | IH3A064 | Y |  |  | ClaudieQ2
|  | IU53024 | Y |  |  | ClaudieQ2
11 |  |  |  | 0
Claudie | XREF_PGM1
|  | IC2B006 | [5 empty] | for INFOX Customer only - No pb for INFOX+KCM
|  | I12696 | Y |  |  | ClaudieQ2
|  | IC2A003 | Y |  |  | ClaudieQ2
|  | IC2C013 | Y |  |  | ClaudieQ2
|  | IH39098 | Y |  |  | ClaudieQ2
|  | IH49040 | Y |  |  | ClaudieQ2
|  | IM93874 | Y |  |  | ClaudieQ2
|  | IM93932 | Y |  |  | ClaudieQ2
|  | PIXRF002 | Y |  |  | ClaudieQ2
9 |  |  |  | 0
Claudie | XREF_PROC1
|  | ID25011 | Y |  |  | ClaudieQ2
|  | IH1A015 | Y |  |  | ClaudieQ2
|  | IH22161 | Y |  |  | ClaudieQ2
|  | IH44087 | Y |  |  | ClaudieQ2
|  | PIXRF003 | Y |  |  | ClaudieQ2
5 |  |  |  | 0
Claudie | XREF_SYSOUT1
|  | IH1A030 | Y |  |  | ClaudieQ2
|  | IH1A154 | Y |  |  | ClaudieQ2
|  | IM90333 | Y |  |  | ClaudieQ2
|  | PIXRF004 | Y |  |  | ClaudieQ2
4 |  |  |  | 0
Total Est. Time (in hours)
Total Est. Days
| Total Number of Scripts | 184
| # of Scripts Converted | 171
| Total for all Quarters | 169
| % Completed | 92.93%
| Total Number of New Scripts | 9
| Analyst | Q1 | Q2 | Q3 | Q4 | Q4
| Claudie | 9 | 69 | 60 | 0 | 1
| Lisa | 1 | 19 | 0 | 0 | 6
| Scott | 0 | 0 | 4 | 0 | 0
| Totals | 10 | 88 | 64 | 0 | 7 | 169 | 169

## Infox-Detail-2010
Suite Totals | Suite | Test Case Document | Converted to MAP | New Scripts | Date | Analyst/Qtr | Comments | Comments
Lisa | A_NISSAN_263
|  | IC53007 | Y |  |  | LisaQ1
|  | IH54039 | Y |  |  | ClaudieQ3 | scott | Ticket 741530
IC55006
|  | IC55006 | N/A |  |  |  |  | Password panel
|  | IC55010 | Y |  |  | ClaudieQ3
|  | IH54029 | Y |  |  | ClaudieQ3
6 |  |  |  | 0
Lisa | QUERY1
|  | IH4B026 | Y |  |  | LisaQ4 |  | Script fails for ticket 742896 in PR290
|  | I12602 | Y |  |  | ClaudieQ3
|  | I12628 | Y |  |  | ClaudieQ3
|  | I12757 | Y |  |  | scottQ3
|  | I724237 |  | 1 |  | LisaQ4 |  | new script for PR300
|  | IH11020 | Y |  |  | scottQ3
|  | IH1A166 | Y |  |  | scottQ3
|  | IH55035 | y |  |  | scottQ3
|  | IU3A008 | Y |  |  | ClaudieQ3
|  | IM92355 | Y |  |  | ClaudieQ3
|  | PIQRY001 | Y |  |  | ClaudieQ3
11
Lisa | REPORTS |  |  | 0
|  | IH54031 | in progress |  |  | Lisa |  | Need to create a popup dropdown list routine
|  | IC11025 | Y |  |  | LisaQ4
|  | IC18007 | Y |  |  | ClaudieQ3
|  | IC1C005 | Y |  |  | ClaudieQ3
|  | IC27001 | Y |  |  | ClaudieQ3
|  | ID12008 | Y |  |  | ClaudieQ3
|  | ID12010 | Y |  |  | ClaudieQ3
|  | IH12106 | Y |  |  | ClaudieQ3
|  | IH1C035 | Y |  |  | ClaudieQ3
|  | IH1C071 | Y |  |  | ClaudieQ3
|  | IH23036 | Y |  |  | ClaudieQ3
|  | IH48061 | Y |  |  | ClaudieQ3 |  | merge h48031 with h48061
|  | IH48075 | Y |  |  | ClaudieQ3 |  | Lisa 11/12/10: updated script for tickets #711140 and #711131 fixed in PR300.
IH49074
|  | IH4B045 | Y |  |  | ClaudieQ3
|  | IH52016 | in progress |  |  | Lisa
|  | IH54012 | Y |  |  | ClaudieQ3
|  | IH55012 | Y |  |  | ClaudieQ3
|  | IH55054 | Y |  |  | ClaudieQ3
|  | IM92493 | Y |  |  | ClaudieQ3 |  | XREF is taking a long time with wild card
|  | IM92538 | Y |  |  | ClaudieQ3
21 |  |  |  | 0
Lisa | SETUP1
|  | I704136 |  | Y |  | LisaQ4
|  | IH48072 | Y |  |  | LisaQ2
|  | IC1B003 | Y |  |  | LisaQ2
|  | IH12135 | Y |  |  | LisaQ2
|  | IH13027 | Y |  |  | ClaudieQ3
IH16065
|  | IH1A097 | Y |  |  | LisaQ2
|  | IH35079 | Y |  |  | LisaQ2
|  | IH3B034 | Y |  |  | LisaQ2
|  | IH46012 | on hold
|  | IH48060 | Y |  |  | ClaudieQ3
|  | IH49009 | Y |  |  | ClaudieQ3
|  | IH4A031 | Y |  |  | ClaudieQ3
|  | IH4A047 | Y |  |  | ClaudieQ3
|  | IH4B007 | Y |  |  | ClaudieQ3
|  | IH4C014 | Y |  |  | ClaudieQ3
|  | IH52034 | Y |  |  | ClaudieQ3
|  | IM92078 | Y |  |  | ClaudieQ3
|  | IM108845 | Y |  |  | ClaudieQ3
|  | P695135 | Y |  |  | ClaudieQ3
19 |  |  |  | 0
Lisa | UPDATE1
|  | IH54062 | Y |  |  | ClaudieQ3
|  | I11903 | Y |  |  | ClaudieQ3
|  | IC1A023 | Y |  |  | ClaudieQ3
|  | IH12176 | Y |  |  | ClaudieQ3
|  | IH12235 | Y |  |  | ClaudieQ3
|  | IH16064 | Y |  |  | ClaudieQ3
|  | IH16151 | Y |  |  | ClaudieQ3
|  | IH21101 | Y |  |  | ClaudieQ3
|  | IH25016 | Y |  |  | ClaudieQ3
|  | IH25036 | Y |  |  | ClaudieQ3
|  | IH3A127 | Y |  |  | ClaudieQ3
|  | IH3C036 | Y |  |  | ClaudieQ3
12 |  |  |  | 0
Lisa | XREF_CICSGROUP1
|  | IH36024 | Y |  |  | ClaudieQ3
IH46042
2 |  |  |  | 0
Lisa | XREF_CICSTRANSACTION1
|  | IH1A028 | Y |  |  | ClaudieQ3
|  | IH35045 | Y |  |  | ClaudieQ3
|  | IH39102 | Y |  |  | ClaudieQ3
|  | IM91489 | Y |  |  | ClaudieQ3
4 |  |  |  | 0
Lisa | XREF_DB2COLLECTIONID1
|  | IM92010 | Y |  |  | LisaQ2
|  | PIXRF008 | Y |  |  | LisaQ2
|  | PI106569 | Y | Y |  | LisaQ2
3 |  |  |  | 1 |  | LisaQ2
Lisa | XREF_DB2PACKAGE1
|  | IH13043 | Y |  |  | LisaQ2
|  | IH12046 | Y |  |  | LisaQ2
|  | PIXRF009 | Y |  |  | ClaudieQ3
3 |  |  |  | 0
Lisa | XREF_DB2PLAN1
|  | IM91549 | Y |  |  | LisaQ2
|  | PIXRF007 | Y |  |  | ClaudieQ3
2 |  |  |  | 0
Lisa | XREF_DB2TABLE1
|  | ID25008 | Y |  |  | LisaQ2
|  | IM90400 | Y |  |  | LisaQ2
|  | PIXRF010 | Y |  |  | ClaudieQ3
3 |  |  |  | 0
Lisa | XREF_DSNAME1
|  | IH49037 | Y |  |  | LisaQ2
|  | IH53002 | Y |  |  | LisaQ2 |  | need function to check # in confirmation panel matches panel list #
|  | PIXRF005 | Y |  |  | ClaudieQ3
|  | PIXRF006 | Y |  |  | ClaudieQ3
4 |  |  |  | 0
Claudie | ADMINISTRATOR
|  | IC4B019 | [5 empty] | installation script
|  | I715736 |  | Y |  | LisaQ4
|  | I10900 | Y |  |  | ClaudieQ2
|  | ID14009 | Y |  |  | ClaudieQ1
|  | IH11045 | Y |  |  | ClaudieQ2
|  | IH12133 | Y |  |  | ClaudieQ1
|  | IH25115 | Y |  |  | ClaudieQ1
|  | IH3A058 | Y |  |  | ClaudieQ2
|  | IH4A016 | Y |  |  | ClaudieQ2
|  | PIADM001 | Y |  |  | ClaudieQ2
|  | PIADM002 | Y |  |  | ClaudieQ2
|  | PIADM003 | Y |  |  | ClaudieQ2
12 |  |  |  | 1
Claudie | XREF_JOB1
|  | IH4A042 | Y |  |  | ClaudieQ2
|  | IC12012 | Y |  |  | ClaudieQ2
|  | IC17008 | Y |  |  | ClaudieQ2
|  | IC3A007 | Y |  |  | ClaudieQ2
|  | IC3A008 | Y | 1 |  | LisaQ4
|  | ID25004 | Y |  |  | ClaudieQ2
|  | ID25006 | Y |  |  | ClaudieQ2
|  | ID25007 | Y |  |  | ClaudieQ2
|  | ID25009 | Y |  |  | ClaudieQ2
|  | ID27005 | Y |  |  | ClaudieQ2
10 |  |  |  | 0
Claudie | FOLDERS
|  | ASSIGN_FOLDER | Y |  |  | ClaudieQ2
|  | IH12021 | Y |  |  | ClaudieQ2
2 |  |  |  | 0
Claudie | MISC1
I12511
|  | I11316 | Y |  |  | ClaudieQ2
|  | IC56006 | Y |  |  | ClaudieQ2
|  | ID17004 | Y |  |  | ClaudieQ2
|  | IH39023 | Y |  |  | ClaudieQ2
|  | IH43143 | Y |  |  | ClaudieQ2
IH47053
|  | IM85804 | Y |  |  | ClaudieQ2
|  | PR715215 | Y | Y |  | ClaudieQ4
8 |  |  |  | 1
Claudie | PRINTSETUP
|  | IH1A122 | Y |  |  | ClaudieQ2
|  | IC13015 | Y |  |  | ClaudieQ2
|  | IC25010 | Y |  |  | ClaudieQ2
|  | IC25011 | Y |  |  | ClaudieQ2
|  | IC27007 | Y |  |  | ClaudieQ2
|  | IH12049 | Y |  |  | ClaudieQ2
|  | IH13053 | Y |  |  | ClaudieQ2
|  | IH17125 | Y |  |  | ClaudieQ2
|  | IH18079 | Y |  |  | ClaudieQ2
|  | IH49031 | Y |  |  | ClaudieQ2
10 |  |  |  | 0
Claudie | SORTS
|  | IH1B052 | Y |  |  | LisaQ2 |  | Infox::verifySortedColumnData function needs updates; Script fails in PR290
|  | IH1C005 | Y | todo new |  | LisaQ2 |  | Script fails in PR290.
IH1B047
|  | IH36020 | Y |  |  | ClaudieQ3
|  | I725695 | Y |  |  | ClaudieQ3
5
Claudie | XREF1
|  | I13095 | Y |  |  | ClaudieQ2
|  | I13095a | Y |  |  | ClaudieQ2
|  | IC13001 | Y |  |  | ClaudieQ2
|  | I13034 | Y |  |  | ClaudieQ2
|  | IH1B022 | Y |  |  | ClaudieQ2
|  | IH45042 | Y |  |  | ClaudieQ2
|  | IM104683 | Y |  |  | ClaudieQ2 |  | Failed in PR290
IM93881
|  | IM90198 | Y |  |  | ClaudieQ2
|  | PIXRF001 | Y |  |  | ClaudieQ2
10 |  |  |  | 0
Claudie | XREF_JOB2
| 11 | IH49035 | Y |  |  | ClaudieQ2
|  | IC53007 | [5 empty] | Password specific
|  | IC53008 | [5 empty] | Password specific
|  | IC56005 | Y |  |  | ClaudieQ2
|  | IH28064 | Y |  |  | ClaudieQ2
|  | IH2B003 | Y |  |  | ClaudieQ2
|  | IH36050 | Y |  |  | ClaudieQ2
|  | IH39051 | Y |  |  | ClaudieQ2
|  | IH39100 | Y |  |  | ClaudieQ2
|  | IH3A064 | Y |  |  | ClaudieQ2
|  | IU53024 | Y |  |  | ClaudieQ2
11 |  |  |  | 0
Claudie | XREF_PGM1
|  | IC2B006 | [5 empty] | for INFOX Customer only - No pb for INFOX+KCM
|  | I12696 | Y |  |  | ClaudieQ2
|  | IC2A003 | Y |  |  | ClaudieQ2
|  | IC2C013 | Y |  |  | ClaudieQ2
|  | IH39098 | Y |  |  | ClaudieQ2
|  | IH49040 | Y |  |  | ClaudieQ2
|  | IM93874 | Y |  |  | ClaudieQ2
|  | IM93932 | Y |  |  | ClaudieQ2
|  | PIXRF002 | Y |  |  | ClaudieQ2
9 |  |  |  | 0
Claudie | XREF_PROC1
|  | ID25011 | Y |  |  | ClaudieQ2
|  | IH1A015 | Y |  |  | ClaudieQ2
|  | IH22161 | Y |  |  | ClaudieQ2
|  | IH44087 | Y |  |  | ClaudieQ2
|  | PIXRF003 | Y |  |  | ClaudieQ2
5 |  |  |  | 0
Claudie | XREF_SYSOUT1
|  | IH1A030 | Y |  |  | ClaudieQ2
|  | IH1A154 | Y |  |  | ClaudieQ2
|  | IM90333 | Y |  |  | ClaudieQ2
|  | PIXRF004 | Y |  |  | ClaudieQ2
4 |  |  |  | 0
Total Est. Time (in hours)
Total Est. Days
| Total Number of Scripts | 178
| # of Scripts Converted | 165
| Total for all Quarters | 163
| % Completed | 92.7%
| Total Number of New Scripts | 4
| Analyst | Q1 | Q2 | Q3 | Q4 | Q4
| Claudie | 3 | 69 | 60 | 0 | 1
| Lisa | 1 | 19 | 0 | 0 | 6
| Scott | 0 | 0 | 4 | 0 | 0
| Totals | 4 | 88 | 64 | 0 | 7 | 163 | 163

## PJW-Detail-2010
Suite Totals | Suite | Test Case Document | Converted to MAP/Quarter/Analyst | New Script (Y/N) |  | Comments
Customize
|  | Customize1 | scottq3
Customize2
2 |  |  |  | 0
Basic Functionality
|  | JCL Editor 1 | scottq3
JCL Editor 2
|  | JMP | scottq3
|  | Local Scan | scottq3
|  | Mainframe Scan | scottq3
|  | Quick Scan | scottq3
6 |  |  |  | 0
Impact Tickets
H5B022
H5B037
H5B249
H5C020
H5C054
H5C053
H5C055
H5C057
H5C058
H15056
H17097
H22083
H22094
H27104
H28009
H31075
H34063
H35013
H41046
H42035
H55021
H57035
H59059
H61041
H61117
H62157
H63123
H64006
H65032
U3B007
U5C010
U5C011
U38015
U55005
U58016
U61004
U61010
U61013
38 |  |  |  | 0
46
| Total Number of Scripts | 46
| # of Scripts Converted | 6
| Total for all Quarters | 6
| % Completed | 13.04%
| Total Number of New Scripts | 0
| Analyst | Q1 | Q2 | Q3 | Q4
| Claudie | 0 | 0 | 0 | 0
| Lisa | 0 | 0 | 0 | 0
| Scott | 0 | 0 | 6 | 0
| Totals | 0 | 0 | 6 | 0 |  | 6